## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-II). | SM/17247 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 4.63 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-II). | SM/17247 | Augmentation | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-II). |  |  | BILL/00156/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-II). | SM/17247 | Augmentation | Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) | Assistant Engineer | Junior Engineer | ORD/000486/2023-2024 | 2338/BQA | 14/08/2023 | 10/05/2024 | SIB SANKAR CHOWDHURY | 227.04 | 160.59 | 70.73 | 81
4 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-II). | SM/17247 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase I)( Zone II) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000513/2023-2024 | 1878/BMD | 17/08/2023 | 15/12/2023 | M/S SAJAHAN CHOWDHURY | 81.74 | 57.09 | 69.84 | 69
5 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-II). | SM/17247 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000281/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 4.63 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-II). | SM/17247 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Sub-Station Equipment and other electromechanical accessories for source Augmentation works for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase I)( Zone II) At Damodhar River Bank site under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001031/2023-2024 | 2963/BMD | 29/02/2024 | 22/08/2025 | COMBINE ENTERPRISES | 28.82 | 0 | 0 | 35
Total | [13 empty] | 347.86 | 217.68 | 62.58