## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for SALMA & Adjoining Mouzas Zone- (I, II & III) Water Supply Scheme. | SM/17248 | Augmentation | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of under Salma (Zone- III) W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora No.of Mouza :- 01 nos, Kendana (Part) Total House Hold- 17 nos. (Part A) | Assistant Engineer | Junior Engineer | ORD/000668/2023-2024 | 808/BSD | 10/08/2023 | 25/08/2023 | RAHUL CHATERJEE | 0.95 | 0.92 | 96.04 | 100
2 | BANKURA |  | Bankura Division | Augmentation works for SALMA & Adjoining Mouzas Zone- (I, II & III) Water Supply Scheme. | SM/17248 | Augmentation | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of under Salma (Zone- III) W/S Scheme and its adyojing mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora No.of Mouza :- 01 nos, Kendana, Total House Hold- 18 nos.(Part B) | Assistant Engineer | Junior Engineer | ORD/000671/2023-2024 | 809/BSD | 10/08/2023 | 25/08/2023 | RAHUL CHATERJEE | 0.95 | 0.92 | 96.35 | 100
3 | BANKURA |  | Bankura Division | Augmentation works for SALMA & Adjoining Mouzas Zone- (I, II & III) Water Supply Scheme. | SM/17248 | Augmentation | Balance work for laying HDPE pipe line from Durlavpur air valve to Durlavpur Muslimpara to increase water pressure at Durlavpur mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone- I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000724/2023-2024 | 825\BSD | 11/08/2023 | 26/08/2023 | SOMA BANERJEE | 0.61 | 0.61 | 100 | 100
4 | BANKURA |  | Bankura Division | Augmentation works for SALMA & Adjoining Mouzas Zone- (I, II & III) Water Supply Scheme. | SM/17248 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.96 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for SALMA & Adjoining Mouzas Zone- (I, II & III) Water Supply Scheme. | SM/17248 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000282/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.96 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for SALMA & Adjoining Mouzas Zone- (I, II & III) Water Supply Scheme. | SM/17248 | Augmentation | Supplying and Laying of HDPE pipeline to increase the water pressure and other allied works at Kukhrakuri Village under Salma (Zone-I) Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora. | Assistant Engineer |  | ORD/001788/2024-2025 | 499/BQA | 25/02/2025 | 27/03/2025 | TAPAS KUMBHAKAR | 6.37 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation works for SALMA & Adjoining Mouzas Zone- (I, II & III) Water Supply Scheme. | SM/17248 | Augmentation | Creation of Balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of SALMA & Adjoining mouzas Zone- (I, II & III) Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora . Total House Hold - 320 nos | Assistant Engineer |  | ORD/000139/2025-2026 | 1297/BQA | 17/06/2025 | 01/08/2025 | EARTH MOVING (INDIA) | 74.56 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation works for SALMA & Adjoining Mouzas Zone- (I, II & III) Water Supply Scheme. | SM/17248 | Augmentation | Augmentation of SALMA & Adjoining mouzas Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000366/2023-2024 | 2028/BQA | 24/07/2023 | 01/07/2025 | PRINCE INDUTRIES (INDIA) | 158.21 | 102.12 | 64.54 | 41
9 | BANKURA |  | Bankura Division | Augmentation works for SALMA & Adjoining Mouzas Zone- (I, II & III) Water Supply Scheme. | SM/17248 | Augmentation | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone- I & II)) under Salma W/S Scheme (BRGF ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Salma (Zone - I) No. of Mouza :- 2 nos, Kukrakuli (Part), Harakbedia (Part), Total House Hold- 19 nos. | Assistant Engineer | Junior Engineer | ORD/000682/2023-2024 | 814/BSD | 10/08/2023 | 25/08/2023 | SONU SINGH | 0.75 | 0.74 | 99.69 | 100
10 | BANKURA |  | Bankura Division | Augmentation works for SALMA & Adjoining Mouzas Zone- (I, II & III) Water Supply Scheme. | SM/17248 | Augmentation | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone- I & II)) under Salma W/S Scheme (BRGF ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block- Chhatna, Name of OHR - Salma (Zone - I), No. of Mouza :- 03 nos, Singhir (Part), Sahebdanga (Part), Bakulia (Part) Total House Hold- 20 nos. | Assistant Engineer | Junior Engineer | ORD/000684/2023-2024 | 815/BSD | 10/08/2023 | 25/08/2023 | SONU SINGH | 0.78 | 0.78 | 99.7 | 100
Total | [13 empty] | 249.09 | 106.08 | 42.59