## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | 'Augmentation works for KALIPUR (Zone - C) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17249 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.7 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | 'Augmentation works for KALIPUR (Zone - C) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17249 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Penchasimul Mouza (Penchasimul & Tentulberiya Vill.) of Kalipur (Zone- C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, (Part-B) | Assistant Engineer | Junior Engineer | ORD/000288/2024-2025 | 645/BSD | 10/06/2024 | 17/06/2024 | INJAMAMUL HAQUE MONDAL | 0.78 | 0 | 0 | 1
3 | BANKURA |  | Bankura Division | 'Augmentation works for KALIPUR (Zone - C) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17249 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Penchasimul Mouza (Penchasimul & Tentulberiya Vill.) of Kalipur (Zone- C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, (Part-C) | Assistant Engineer | Junior Engineer | ORD/000289/2024-2025 | 646/BSD | 10/06/2024 | 17/06/2024 | INJAMAMUL HAQUE MONDAL | 0.77 | 0 | 0 | 1
4 | BANKURA |  | Bankura Division | 'Augmentation works for KALIPUR (Zone - C) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17249 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Penchasimul Mouza (Penchasimul & Tentulberiya Vill.) of Kalipur (Zone- C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Kalipur, Total House Hold - 06 nos (Part-A) | Assistant Engineer | Junior Engineer | ORD/000286/2024-2025 | 644/BSD | 10/06/2024 | 17/06/2024 | MOHAMMED RAFIK MANDAL | 0.89 | 0 | 0 | 1
5 | BANKURA |  | Bankura Division | 'Augmentation works for KALIPUR (Zone - C) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17249 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000284/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.7 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | 'Augmentation works for KALIPUR (Zone - C) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17249 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Kalipur (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Jal Jeevan Mission under Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - KALIPUR, Total House Hold - 250 nos. | Assistant Engineer | Junior Engineer | ORD/000803/2022-2023 | 711/BQA | 30/03/2023 | 01/01/2026 | APEX ENTERPRISE | 99.27 | 0 | 0 | 32
Total | [13 empty] | 107.13 | 0 | 0