## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | 'Augmentation works for TILNA (Zone - E) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17250 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.25 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | 'Augmentation works for TILNA (Zone - E) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17250 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Tilna (Zone-E) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000844/2023-2024 | 2970/BQA | 31/10/2023 | 30/11/2023 | GEO SOLUTION | 2.68 | 2.02 | 75.38 | 100
3 | BANKURA |  | Bankura Division | 'Augmentation works for TILNA (Zone - E) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | SM/17250 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000286/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.25 | 0 | 0 | 0
Total | [13 empty] | 5.18 | 2.02 | 38.98