## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17251 | Augmentation | Work Order for Supply, Delivery and Stacking of Air Valve of Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000124/2023-2024 | 126/KSD | 25/05/2023 | 09/06/2023 | SSPR VALVE MANUFACTURING PVT. LTD. | 0.94 | 0.94 | 100 | 20
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17251 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Makhnu (Zone- K) ( boosting at tail end) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block : Ranibandh , Dist: Bankura | Driller-in-Charge | Junior Engineer | ORD/000150/2024-2025 | 493/BMD | 09/07/2024 | 05/03/2025 | M/S BIPUL BANERJEE | 49.9 | 9.41 | 18.85 | 76
3 | BANKURA |  | Bankura Division | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17251 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000175/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 1.42 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17251 | Augmentation | Raniabndh -Jhilimili Road from Ch.1.860 km to Ch. 1.890 km, from Ch. 2.264 km to Ch. 2.284 hm, from Ch. 3.309 km to Ch. 3.609 km and from Ch. 3.630¿km to Ch. 3.770 km, Restoration work damage by PHE Dept by laying pipe line under Bankura Highway Division in the district of Bankura. Augmentation of Makhnu (Zone-K) W/S Scheme (SM/17251) |  |  | BILL/01247/2024-2025 | BP-347/2024-25 | 03/10/2024 | 03/10/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 1.91 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17251 | Augmentation | New service connection charge at T/W-III of Makhnu. |  |  | BILL/01148/2024-2025 | BP-2024-25-284 | 21/11/2024 | 21/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.98 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17251 | Augmentation | Raniabndh -Jhilimili Road from Ch.1.860 km to Ch. 1.890 km, from Ch. 2.264 km to Ch. 2.284 hm, from Ch. 3.309 km to Ch. 3.609 km and from Ch. 3.630¿km to Ch. 3.770 km, Restoration work damage by PHE Dept by laying pipe line under Bankura Highway Division in the district of Bankura. Augmentation of Makhnu (Zone-K) W/S Scheme (SM/17251) |  |  | BILL/01029/2024-2025 |  | 28/09/2024 | 28/09/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 1.91 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17251 | Augmentation | New service connection charge at T/W-IV of Makhnu |  |  | BILL/01150/2024-2025 | BP-2024-25-285 | 19/11/2024 | 19/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.47 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17251 | Augmentation | Sinking of 3 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-K (Makhnu) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000791/2022-2023 | 675/BQA | 28/03/2023 | 17/02/2027 | GOUTAM BHATTACHRYYA | 75.44 | 29.37 | 38.93 | 65
9 | BANKURA |  | Bankura Division | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17251 | Augmentation | Sinking of 2 (Two) Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction of 4 (Four) Nos. Pump Houses with ancillary works in different mouzas of Zone-K (Makhnu) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001154/2023-2024 | 358/BQA | 06/02/2024 | 07/03/2024 | SUBHADIP KOLE | 37.55 | 1.35 | 3.59 | 30
10 | BANKURA |  | Bankura Mechanical | Augmentation works for Makhnu (Zone- K) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17251 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Makhnu (Zone k) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Driller-in-Charge | Junior Engineer | ORD/000418/2025-2026 | 579/BMD | 03/07/2025 | 01/10/2025 | GOENKA ENTERPRISE | 28.19 | 0 | 0 | 0
Total | [13 empty] | 200.7 | 41.06 | 20.46