## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Baksibandh(Zone - J) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/17252 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.86 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for Baksibandh(Zone - J) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/17252 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000288/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.86 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Baksibandh(Zone - J) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/17252 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Boxibandh (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Jal Jeevan Mission under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Boxibandh, Total House Hold - 621 nos. | Assistant Engineer | Junior Engineer | ORD/000685/2022-2023 | 586/BQA | 20/03/2023 | 01/04/2026 | M/S TARUN KUMAR PATRA | 90.34 | 10.3 | 11.4 | 12
4 | BANKURA |  | Bankura Division | Augmentation works for Baksibandh(Zone - J) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/17252 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Bakshibandh (Zone ¿ J) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000381/2024-2025 | 2436/BQA | 25/09/2024 | 25/10/2024 | CARTO | 2.21 | 0 | 0 | 80
Total | [13 empty] | 96.27 | 10.3 | 10.7