## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation works for Agarda and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17253 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Agarda & its adjoining Mouzas water supply scheme under onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer |  | ORD/000544/2023-2024 | 1980/BMD | 28/08/2023 | 26/12/2023 | TAPAN KUMAR SARKAR | 56.61 | 0 | 0 | 64
2 | BANKURA |  | Bankura Division | Augmentation works for Agarda and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17253 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.96 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Agarda and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17253 | Augmentation | Augumentation of Agarda and adjoining Mouzas Water Supply Scheme under Onda (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000365/2023-2024 | 2027/BQA | 24/07/2023 | 19/04/2024 | UNIVERSAL CONSTRUCTION | 212.34 | 0 | 0 | 70
4 | BANKURA |  | Bankura Division | Augmentation works for Agarda and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17253 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000289/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.96 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for Agarda and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17253 | Augmentation | Construction of Low Lift Pump House, Laying additional LDS and Construction of Boundary Wall at Jadab Nagar under Augmentation works for Agarda and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/000194/2024-2025 | 1866/BQA | 12/07/2024 | 01/04/2026 | SOUMITRA KUMAR DAS | 34.71 | 0 | 0 | 90
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Agarda and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17253 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at existing Tubewell for Augmentation of Agarda and adjoining mouzas piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur Dist: Bankura | Assistant Engineer | Estimator,Junior Engineer | ORD/000167/2024-2025 | 509/BMD | 09/07/2024 | 04/07/2025 | CHAKRABORTY MINING & ENGINEERING. | 24.55 | 0 | 0 | 100
Total | [13 empty] | 334.14 | 0 | 0