## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Work Order for Interconnection of newly laid pipeline and existing pipeline near Arkama village of Augmentation works for Arkama (Zone- H) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer |  | ORD/000446/2023-2024 | 254/KSD | 24/08/2023 | 31/08/2023 | M/S SUPRIYA CHATTERJEE | 0.95 | 0 | 0 | 20
2 | BANKURA |  | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Work Order for Interconnection of newly laid pipeline and existing pipeline near Sindurpeti village of Augmentation works for Arkama (Zone- H) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000450/2023-2024 | 258/KSD | 24/08/2023 | 31/08/2023 | GOURANGA CHATTERJEE | 0.7 | 0 | 0 | 20
3 | BANKURA |  | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Work Order for Interconnection of newly laid pipeline and existing pipeline near Arkama village of Augmentation works for Arkama (Zone- H) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer |  | ORD/000448/2023-2024 | 256/KSD | 24/08/2023 | 31/08/2023 | M/S SUPRIYA CHATTERJEE | 0.7 | 0 | 0 | 20
4 | BANKURA |  | Bankura Mechanical | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of High lift and Low Lift Pumping machineries with other electro-mechanical accessories at tail end and CWR site for for Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) under Bankura Mechanical Division, PHE Dte. Block : Khatra , Dist: Bankura | Driller-in-Charge | Junior Engineer | ORD/000169/2024-2025 | 511/BMD | 09/07/2024 | 06/11/2024 | RAJIB COMPANY | 44.01 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-H (Arkama) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000801/2022-2023 | 726/BQA | 30/03/2023 | 14/05/2023 | UTTAM KUMAR SINHAMAHAPATRA | 48.95 | 0 | 0 | 100
6 | BANKURA |  | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Laying HDPE pipeline to increase pressure in Damodarpur Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) of Zone-H (Arkama) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001126/2023-2024 | 247/BQA | 25/01/2024 | 24/02/2024 | BIKASH MANDAL | 5.11 | 0 | 0 | 80
7 | BANKURA |  | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000169/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 2.96 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Sinking of 2 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine), Construction of 1 No. CWR at OHR site, Construction of 1 No. Pump House at Tubewell site, Laying of pipeline and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Augmentation works for Zone-H (Arkama) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000066/2024-2025 | 1521/BQA | 19/06/2024 | 19/07/2024 | SINGHA ENTERPRISE | 51.88 | 0 | 0 | 70
9 | BANKURA |  | Bankura Mechanical | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of High lift and Low Lift Pumping machineries with other electro-mechanical accessories at CWR site for for Augemention works for Arkama (zone H) Under Khatra Hirbandh Ranibandh Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block Khatra , Dist Bankura | Driller-in-Charge | Junior Engineer | ORD/000880/2024-2025 | 2040/BMD | 07/03/2025 | 05/07/2025 | M/S TARUN KUMAR PATRA | 42.61 | 0 | 0 | 0
10 | BANKURA |  | Bankura Mechanical | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) | SM/17254 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Arkama (Zone H) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura | Driller-in-Charge | Junior Engineer | ORD/000043/2025-2026 | 247/BMD | 14/05/2025 | 12/08/2025 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 29.11 | 0 | 0 | 0
Total | [13 empty] | 226.98 | 0 | 0