## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | SM/17258 | Augmentation | Supplying of different dia. CIDF sluice valve PN- 1.0 in connection with Jal Jeevan Mission (JJM) of Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A,B,C & D) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000713/2022-2023 | 621/BQA | 23/03/2023 | 22/04/2023 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.52 | 3.76 | 50 | 20
2 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | SM/17258 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.29 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | SM/17258 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-D) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000716/2023-2024 | 2173/BMD | 30/10/2023 | 27/02/2024 | PRADIP KUMAR DHABAL | 32.67 | 21.75 | 66.58 | 60
4 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | SM/17258 | Augmentation | Augmentation for Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-D) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000396/2023-2024 | 2081/BQA | 27/07/2023 | 22/04/2024 | MUNMUN UPADHYAY | 127.08 | 80.05 | 62.99 | 98
5 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | SM/17258 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000292/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.29 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | SM/17258 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of MCC Panel and other electromechanical acessories w for Augmentation works for Aguri Band Punisol and its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Estimator | ORD/000323/2024-2025 | 864/BMD | 29/08/2024 | 24/08/2025 | AMITAVA CHAKRABORTY | 35.75 | 0 | 0 | 90
Total | [13 empty] | 205.59 | 105.56 | 51.35