## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | SM/17258 | Augmentation | Supplying of different dia. CIDF sluice valve PN- 1.0 in connection with Jal Jeevan Mission (JJM) of Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-A,B,C & D) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000713/2022-2023 | 621/BQA | 23/03/2023 | 22/04/2023 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.52 | 3.76 | 50 | 20
2 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | SM/17258 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.29 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | SM/17258 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-D) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000716/2023-2024 | 2173/BMD | 30/10/2023 | 27/02/2024 | PRADIP KUMAR DHABAL | 32.67 | 21.75 | 66.58 | 60
4 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | SM/17258 | Augmentation | Augmentation for Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-D) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000396/2023-2024 | 2081/BQA | 27/07/2023 | 22/04/2024 | MUNMUN UPADHYAY | 127.08 | 80.05 | 62.99 | 98
5 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | SM/17258 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000292/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.29 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | SM/17258 | Augmentation | Sinking of 1 (one) nos 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method and Repairing and Renovation of RCC Elevated Over Head Reservoir of 350 Cum capacity under Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-D) under Onda Water Supply Scheme (BRGF Ph-I) | Assistant Engineer | Junior Engineer | ORD/001393/2024-2025 | 40/BQA | 02/01/2025 | 03/04/2026 | MUNMUN UPADHYAY | 26.62 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | SM/17258 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of MCC Panel and other electromechanical acessories w for Augmentation works for Aguri Band Punisol and its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Estimator | ORD/000323/2024-2025 | 864/BMD | 29/08/2024 | 24/08/2025 | AMITAVA CHAKRABORTY | 35.75 | 0 | 0 | 90
8 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). | SM/17258 | Augmentation | Sinking of 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of Chinganiand adjoining mouzas W/S Scheme & Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- D) under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001939/2024-2025 | 655/BQA | 11/03/2025 | 05/06/2025 | SWAPAN KUMAR BIT | 12.23 | 0 | 0 | 0
Total | [13 empty] | 244.43 | 105.56 | 43.19