## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- E) under Onda Block (BRGF Ph - I Project). | SM/17259 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-E) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000548/2023-2024 | 1984/BMD | 28/08/2023 | 26/12/2023 | EASTERN INDIA SALES & SERVICE | 74.01 | 44.3 | 59.86 | 60
2 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- E) under Onda Block (BRGF Ph - I Project). | SM/17259 | Augmentation | Schedule for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿¿& parallel pipe line to increase pressure in connection with Jal Jeevan Mission (JJM) of Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-E) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000382/2023-2024 | 2043/BQA | 24/07/2023 | 19/04/2024 | GOPAL CHANDRA CHOWDHURY | 395 | 394.38 | 99.84 | 100
3 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- E) under Onda Block (BRGF Ph - I Project). | SM/17259 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 14.5 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- E) under Onda Block (BRGF Ph - I Project). | SM/17259 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of CWPH Pumping machineries with other electro mechanical accessories for Augmentation of Aguri bandh Punisole and its adjoining mouzas water supply scheme (Zone E) under Onda Block (BRGF Ph-I) at CWR site Nischintapur under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001076/2023-2024 | 3055/BMD | 12/03/2024 | 05/07/2025 | M.S. ENTERPRISE | 77.57 | 27.13 | 34.98 | 100
5 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- E) under Onda Block (BRGF Ph - I Project). | SM/17259 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000293/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 14.5 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for Aguri Band Punisol & its adjoining Mouzas Water Supply Scheme (Zone- E) under Onda Block (BRGF Ph - I Project). | SM/17259 | Augmentation | Sinking of 02 (Two) nos. Tubewell, 03 (Three) nos. rotary tubewell with low lift pump houses, construction of 250 cum. CWR with high lift Pumphouse, Repairing and Renovation of 700 Cum. OHR, construction of Boundary wall, WBSEDCEL Room, Operator's room cum Guard room and Laying HDPE pipe line from CWR site to Punisol mouza under Augmentation works for Aguri Band Punisol and adjoining Mouzas Water Supply Scheme (Zone-E) under Onda block (BRGF Ph-I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001961/2024-2025 | 696/BQA | 12/03/2025 | 26/09/2026 | PRADIP PATRA | 236.76 | 0 | 0 | 8
Total | [13 empty] | 812.34 | 465.81 | 57.34