## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Zone- Malian under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17260 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone- Malian in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000607/2022-2023 | 560/BQA | 17/03/2023 | 01/05/2023 | PARESH CHANDRA LAYEK | 32.12 | 0 | 0 | 100
2 | BANKURA |  | Bankura Division | Augmentation works for Zone- Malian under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17260 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000172/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 1.23 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Zone- Malian under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17260 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Deuli (Zone Malian ) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Driller-in-Charge | Junior Engineer | ORD/000057/2025-2026 | 253/BMD | 14/05/2025 | 12/08/2025 | SINHA ELECTRICALS | 27.35 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Zone- Malian under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17260 | Augmentation | Sinking of 2 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine), Construction of 2 Nos. pump house at tubewell site, laying distribution pipeline and providing FHTC of Zone-Malian in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000085/2025-2026 | 1120/BQA | 07/05/2025 | 06/07/2025 | UNIVERSAL CONSTRUCTION | 26.03 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Zone- Malian under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17260 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Submersible Pump motor set other allied works at Zone Malian OHR under Khatra-Hirbandh-Ranibandh Water Supply Scheme BMD, PHE Dte | Driller-in-Charge | Junior Engineer | ORD/000197/2025-2026 | 643/BMD | 11/07/2025 | 09/10/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 35.2 | 0 | 0 | 0
Total | [13 empty] | 121.93 | 0 | 0