## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Bhulanpur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17261 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.82 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Bhulanpur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17261 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation of Bhulanpur and adjoining mouzas water supply scheme (BRGF Ph I) Block Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001080/2023-2024 | 3059/BMD | 12/03/2024 | 08/09/2024 | GOENKA ENTERPRISE | 42.08 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Bhulanpur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17261 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000295/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.82 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Bhulanpur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17261 | Augmentation | Augumentation of Bhulanpur and adjoining Mouzas Water Supply Scheme under Onda (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000474/2023-2024 | 2329/BQA | 14/08/2023 | 27/12/2025 | PRADIP PATRA | 200.88 | 0 | 0 | 50
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Bhulanpur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17261 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Bhulanpur and its and its adjoining Mouzas water supply scheme under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000549/2023-2024 | 1985/BMD | 28/08/2023 | 15/12/2025 | UNIVERSAL ENTERPRISE | 53.98 | 0 | 0 | 80
6 | BANKURA |  | Bankura Division | Augmentation works for Bhulanpur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17261 | Augmentation | Construction of low lift Pump House and Boundary Wall under Augmentation of Bhulanpur Water Supply Scheme | Assistant Engineer | Junior Engineer | ORD/000191/2024-2025 | 1862/BQA | 12/07/2024 | 01/04/2025 | M/S SUPRIYA CHATTERJEE | 14.51 | 0 | 0 | 100
Total | [13 empty] | 317.1 | 0 | 0