## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Jamadhara and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). | SM/17262 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.03 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for Jamadhara and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). | SM/17262 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000294/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.03 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Jamadhara and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). | SM/17262 | Augmentation | Augumentation of Jamadhara and adjoining Mouzas Water Supply Scheme under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000497/2023-2024 | 2347/BQA | 14/08/2023 | 01/11/2025 | SWAPAN KUMAR UPADHYAY | 198.08 | 0 | 0 | 70
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Jamadhara and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). | SM/17262 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Jamdhara & its adjoining Mouzas water supply scheme under onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Estimator,Junior Engineer | ORD/000541/2023-2024 | 1977/BMD | 28/08/2023 | 19/04/2025 | GOENKA ENTERPRISE | 56.67 | 22.22 | 39.21 | 75
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Jamadhara and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph- I Project). | SM/17262 | Augmentation | Submission of quotation for new service connection at Jamdhara w/s scheme. mouza-Bhedua.SM/17262 |  |  | BILL/01353/2024-2025 | BP-2024-25-337 | 29/01/2025 | 29/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.57 | 0 | 0 | 0
Total | [13 empty] | 263.39 | 22.22 | 8.43