## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17280 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17280 | Augmentation | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). |  |  | BILL/00129/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17280 | Augmentation | Augumentation of Nikunjapur and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000400/2023-2024 | 2085/BQA | 27/07/2023 | 17/01/2025 | DIVINE | 177.02 | 138.23 | 78.09 | 80
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17280 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Nikanjapur & Adjoining mouza water supply scheme (Zone-A) (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Onda , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000553/2023-2024 | 1989/BMD | 28/08/2023 | 26/12/2023 | DEBJYOTI BASU | 60.81 | 29.87 | 49.13 | 70
5 | BANKURA |  | Bankura Division | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17280 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000290/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.5 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17280 | Augmentation | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). |  |  | BILL/01628/2023-2024 | BP-2023-24-156 | 19/03/2024 | 19/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.65 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17280 | Augmentation | Total payable load enhancement charges at Angariaof Nikunjapur Zone-A ws scheme under BMD PHED. |  |  | BILL/00292/2024-2025 | BP-2024-25-98 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.09 | 0 | 0 | 0
8 | BANKURA |  | Bankura Mechanical | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17280 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of CWPH Pumping machineries with other electro-mechanical accessories for Augmentation of Nikanjapur & Adjoining mouza water supply scheme (Zone-A) (BRGF Phase I) at CWR site Gamirda under Bankura Mechanical Division, PHE Dte. Block : Onda , Dist: Bankura | Assistant Engineer | Estimator,Junior Engineer | ORD/001077/2023-2024 | 3056/BMD | 12/03/2024 | 05/07/2025 | M.S. ENTERPRISE | 40.56 | 0 | 0 | 95
9 | BANKURA |  | Bankura Division | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17280 | Augmentation | Construction of Low Lift Pump House and Boundary Wall at Gamidya Mouza under Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Block (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/001405/2024-2025 | 48/BQA | 02/01/2025 | 01/12/2025 | GOURANGA NANDI | 14.49 | 0 | 0 | 80
Total | [13 empty] | 304.13 | 168.11 | 55.27