## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme |  |  | BILL/00213/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme |  |  | BILL/00195/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000182/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 4 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | New service connection for Gargaria water supply scheme under Bankura Mechanical Division PHE Dte. |  |  | BILL/00384/2024-2025 | BP-2024-25-87 | 11/06/2024 | 11/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.43 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | New service connection for Gargaria water supply scheme under Bankura Mechanical Division Dte. |  |  | BILL/00383/2024-2025 | BP-2024-25-84 | 11/06/2024 | 11/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | New 3 phase service connection for site Gargaria Zone A |  |  | BILL/00697/2024-2025 | BP-2024-25-163 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | New 3 phase service connection for site Gargaria Zone A |  |  | BILL/00698/2024-2025 | BP-2024-25-168 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.43 | 0 | 0 | 0
8 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | Acceptance cum Formal work order for the work of Providing installation of High lift Pumping machineries with allied works for Augmentation works for Gargariya Zone B water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme under Bankura Mechanical Division, P.H.E. Dte | Driller-in-Charge | Junior Engineer | ORD/000321/2024-2025 | 862/BMD | 29/08/2024 | 26/04/2025 | TAPAN KUMAR SARKAR | 34.3 | 0 | 0 | 70
9 | BANKURA |  | Bankura Division | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | Construction of 2 (Two) Nos. Boundary wall at Tubewell site for Augmentation of Water Supply Scheme for Gargaria, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000079/2025-2026 | 1018/BQA | 25/04/2025 | 24/06/2025 | GON ASSOCIATES | 15.45 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR, Repairing and painting of High lift Pump House, Operator Room, Clear Water Reservoir, WBSEDCL Room, Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Gargaria, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000261/2025-2026 | 1542/BQA | 14/07/2025 | 12/09/2025 | SAYED PAHALOWAN | 27.95 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | Work Order for Installation of scheme information board for 4 nos. site of Augmentation works for Gargariya, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) [SM/17281] and 2 nos. site of Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas (SM/17707) within Sarenga Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Contractual) | ORD/001919/2024-2025 | 163\KSD | 07/03/2025 | 17/03/2025 | SUBHADIP KOLE | 0.9 | 0 | 0 | 90
12 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Gargariya Zone-A water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000573/2023-2024 | 2029/BMD | 01/09/2023 | 06/08/2026 | S.P. CONSTRUCTION | 90.11 | 0 | 0 | 30
13 | BANKURA |  | Bankura Mechanical | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | SM/17281 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of HL Pumping machineries with illumination system other electromechanical accessories for Augmentation for Gargariya Zone-A and adjoining mouzas under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000172/2024-2025 | 514/BMD | 09/07/2024 | 01/03/2026 | S.P. CONSTRUCTION | 78.81 | 0 | 0 | 20
Total | [13 empty] | 267.73 | 0 | 0