## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17282 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.85 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17282 | Augmentation | MS Pipe line inter connection between Submersible pump to OHR and construction of sluice valve chamber of Puncha and adjoining Mouzas Water Supply Scheme (Zone-A,B & C) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. SM/09529 |  | Junior Engineer | ORD/000499/2022-2023 | 377/BQA | 23/02/2023 | 09/04/2023 | SAMIRUDDIN KHAN | 5.4 | 2.39 | 44.26 | 100
3 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17282 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000287/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.85 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17282 | Augmentation | Submission of quotation for load enhancement at Banshdanga under BMD, PHE dte. |  |  | BILL/00289/2024-2025 | 1 | 06/06/2024 | 06/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.95 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17282 | Augmentation | Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000297/2023-2024 | 1915/BQA | 13/07/2023 | 01/01/2026 | APEX ENTERPRISE | 224.56 | 180.21 | 80.25 | 90
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17282 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Puncha & its adjoining Mouzas water supply scheme (Zone-A) under onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000555/2023-2024 | 1991/BMD | 28/08/2023 | 19/04/2025 | ABHIJIT MUKHERJEE | 47.76 | 24.56 | 51.44 | 10
7 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17282 | Augmentation | Construction of Boundary wall in connection with Jal Jeevan Mission (JJM) for Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte.. (Total Length:- 120mtr.). | Assistant Engineer |  | ORD/000077/2025-2026 | 1016/BQA | 25/04/2025 | 24/07/2025 | RUFIKUL MONDAL | 14.32 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17282 | Augmentation | Laying of HDPE Pipe line for Mouleswar,Khamarberiya,Datina,Datina purusatampur,Gogra & Jamra madhabpur Mouzas under Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000161/2025-2026 | 1302/BQA | 17/06/2025 | 01/01/2026 | SHYAMAL KUMAR DAS | 45.45 | 0 | 0 | 0
Total | [13 empty] | 344.13 | 207.16 | 60.2