## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17283 | Augmentation | Construction & commissioning of FHTC (Functional House Hold Tap Connection) in different mouzas for Augmentation of Water Supply Scheme for Mandalkuli, Zone-IIIA and its adjoining Mouzas under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000324/2023-2024 | 1928/BQA | 13/07/2023 | 01/01/2026 | EARTH MOVING (INDIA) | 116.45 | 58.53 | 50.26 | 20
2 | BANKURA |  | Bankura Mechanical | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17283 | Augmentation | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme |  |  | BILL/00215/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17283 | Augmentation | Acceptance cum Formal work order for the work of Modification and up gradation of Gaseous chlorination system at Head work site under Augmentation work of Mandalkuli (zone IIIA ) of Raipur water supply scheme (BRGF Phase I) under JJM , under Bankura Mechanical Division ,PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001033/2023-2024 | 2965/BMD | 29/02/2024 | 27/08/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 14.2 | 14.14 | 99.59 | 98
4 | BANKURA |  | Bankura Division | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17283 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000191/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 3.7 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17283 | Augmentation | Acceptance cum Formal work order for the work of Augmentation work for Mandalkuli (Zone IIIA) of Raipur water supply scheme under Bankura Mechanical Division, P.H.E. Dte | Driller-in-Charge | Estimator | ORD/000878/2024-2025 | 2038/BMD | 07/03/2025 | 05/07/2025 | GOENKA ENTERPRISE | 63.94 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17283 | Augmentation | Construction of Boundary wall, Construction of Operator room and WBSEDCL room of Mandalkuli (Zone- IIIA) of Raipur Water Supply Scheme (BRGF Ph-I)) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000176/2025-2026 | 1312/BQA | 17/06/2025 | 15/09/2025 | COSMIC CONSTRUCTION | 39.9 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17283 | Augmentation | Acceptance cum Formal work order for the work of Supply installation of riverbed submersible pump motor and allied work for augmentation work at Mandalkuli (IIIA) under Raipur Block sub Surface Water Based Piped Water Supply Scheme , under Bankura Mechanical Division PHE Dte | Driller-in-Charge | Junior Engineer | ORD/000015/2025-2026 | 150/BMD | 30/04/2025 | 25/01/2026 | PRADIP KUMAR DHABAL | 32.25 | 0 | 0 | 10
8 | BANKURA |  | Bankura Division | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17283 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 450 Cum., staging height 20 Mtr.), High lift Pump House, Operator Room, Clear Water Reservoir, WBSEDCL Room, Chlorination Room, Guard Room, Boundary Wall, laying distribution pipeline to provide FHTC, Sinking of 6 (Six) Nos. 200 mm dia. X 5.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with all allied works of Augmentation works for Mandalkuli, Zone-IIIA Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000126/2025-2026 | 1288/BQA | 17/06/2025 | 18/12/2025 | SUBHENDU SEKHAR GORAI | 96.65 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17283 | Augmentation | Work Order for Installation of scheme information board for 2 nos. site of Augmentation of Water Supply Scheme for Mandalkuli (Zone-IIIA) [SM/17283], 1 no. site of Augmentation of Water Supply Scheme for Mandalkuli (Zone-IIIB) [SM/17435] and 2 nos. site of Augmentation of Water Supply Scheme for Dhemushunya (Zone-IV) [SM/17714] within Raipur Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001933/2024-2025 | 176\KSD | 07/03/2025 | 17/03/2025 | M/S ASHOK KUMAR DEY | 0.75 | 0 | 0 | 90
Total | [13 empty] | 369.34 | 72.67 | 19.68