## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17284 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Damodarbati (228), Jamdoba (229), , Baruipara (236), Teliberia (238), Kalyari (240), Patpur (241) & Mauchura (242) mouzas by retrofitting Puncha and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte.Total Household-122 NOS | Assistant Engineer | Junior Engineer | ORD/000149/2023-2024 | 1349/BQA | 02/06/2023 | 01/08/2023 | SIB SANKAR CHOWDHURY | 24.06 | 0 | 0 | 100
2 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17284 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.8 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17284 | Augmentation | MS Pipe line inter connection between Submersible pump to OHR and construction of sluice valve chamber of Puncha and adjoining Mouzas Water Supply Scheme (Zone-A,B & C) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. SM/09529 |  | Junior Engineer | ORD/000499/2022-2023 | 377/BQA | 23/02/2023 | 09/04/2023 | SAMIRUDDIN KHAN | 5.4 | 0 | 0 | 100
4 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17284 | Augmentation | Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000296/2023-2024 | 1914/BQA | 13/07/2023 | 01/04/2026 | GOUTAM BHATTACHRYYA | 234.49 | 0 | 0 | 95
5 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17284 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000285/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.8 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17284 | Augmentation | Submission of quotation money for load enhancement at Puncha Teliberia under BMD, PHE Dte. |  |  | BILL/00296/2024-2025 | BP-2024-25-60 | 24/07/2024 | 24/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.94 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17284 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Puncha & its adjoining Mouzas water supply scheme (Zone-B) under onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 2122/BMD | 22/09/2023 | 16/09/2025 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 75.09 | 0 | 0 | 45
8 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17284 | Augmentation | Crossing Rail Track ( South Eastern RLY. K.M. 204/13 -15) in between Ramsagar Rly. Station and Bishnupur Rly. station in Sur Managar mouza, P.S. Bankura,by HDD method with 300 mm (OD) MS Casing Pipe with 150 mm dia. MS carrier pipe for distribution pipe under Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-C) & Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/002046/2024-2025 | 683/BQA | 12/03/2025 | 11/05/2025 | M/S TARUN KUMAR PATRA | 47.19 | 0 | 0 | 0
Total | [13 empty] | 390.78 | 0 | 0