## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17285 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 12.66 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17285 | Augmentation | MS Pipe line inter connection between Submersible pump to OHR and construction of sluice valve chamber of Puncha and adjoining Mouzas Water Supply Scheme (Zone-A,B & C) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. SM/09529 |  | Junior Engineer | ORD/000499/2022-2023 | 377/BQA | 23/02/2023 | 09/04/2023 | SAMIRUDDIN KHAN | 5.4 | 0 | 0 | 100
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17285 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Puncha & its adjoining Mouzas water supply scheme (Zone-C) under onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000556/2023-2024 | 1992/BMD | 28/08/2023 | 26/12/2023 | MENAKA ENTERPRISE | 41.73 | 0 | 0 | 60
4 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17285 | Augmentation | Sinking of 2 (two) nos 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method and Repairing and Renovation of RCC Elevated Over Head Reservoir of 500 Cum capacity under Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-C) under Onda Water Supply Scheme (BRGF Ph-I). | Assistant Engineer |  | ORD/000352/2024-2025 | 2347/BQA | 09/09/2024 | 09/10/2024 | SUBHANKAR BANERJEE | 43.54 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17285 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000283/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 12.66 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17285 | Augmentation | Wayleave/Track crossing proposal with application ID:SER-ADRA-WL-14 For Puncha (zone-c) SM Code-SM/SM/17285 |  |  | BILL/00059/2024-2025 | FHTC/04 | 26/04/2024 | 26/04/2024 | SOUTH EASTERN RAILWAY | 0.1 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17285 | Augmentation | Submission of quotation for load enhancement at mouza Shingahati of Puncha zone C ws scheme under BMD PHED. |  |  | BILL/00288/2024-2025 | BP-2024-25-59 | 24/07/2024 | 24/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.94 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17285 | Augmentation | Payment of Wayleave fecility charges of PUNCHA (ZONE-C) W/S Scheme. Scheme Code-SM/17285. Application ID-SER-ADRA-2024-WL-14 |  |  | BILL/00274/2024-2025 | BP-114/2024-25 | 19/06/2024 | 19/06/2024 | SOUTH EASTERN RAILWAY | 5.64 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17285 | Augmentation | Creation of FHTC (Functional House Hold Tap Connection)¿& parallel pipe line in connection with Jal Jeevan Mission (JJM) for Augmentation of Puncha and adjoining Mouzas Water Supply Scheme (Zone-C) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000321/2023-2024 | 1925/BQA | 13/07/2023 | 01/03/2026 | M/S TARUN KUMAR PATRA | 353.11 | 0 | 0 | 82
10 | BANKURA |  | Bankura Division | Augmentation works for Puncha & its adjoining Mouzas Water Supply Scheme (Zone- C) under Onda Block (BRGF Ph - I Project). | SM/17285 | Augmentation | Balance allied works of Augmentation of Puncha and its adjoining Mouzas Water Supply Scheme (Zone-C) under Onda Water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub-Division of BANKURA Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000184/2024-2025 | 1814/BQA | 11/07/2024 | 01/02/2026 | M/S TARUN KUMAR PATRA | 125.34 | 0 | 0 | 85
Total | [13 empty] | 601.13 | 0 | 0