## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17286 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Ratanpur( Zone-A) Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block : Bankura-I ,Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000557/2023-2024 | 1993/BMD | 28/08/2023 | 26/12/2023 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 33.54 | 0 | 0 | 76
2 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17286 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.8 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17286 | Augmentation | Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone-A)under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000466/2023-2024 | 2321/BQA | 14/08/2023 | 10/05/2024 | APURBA PATRA | 135.51 | 0 | 0 | 70
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17286 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of HL pumping machineries and other electromechanical accessories at CWPH for Augmentation of Ratanpur Zone -A and adjoining mouzas water supply scheme (BRGF Ph-I) Block -Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Estimator,Junior Engineer | ORD/001100/2023-2024 | 3075/BMD | 12/03/2024 | 10/07/2024 | INDRAJIT MITRA | 15.85 | 0 | 0 | 100
5 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17286 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000280/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.8 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | SM/17286 | Augmentation | Construction of Low Lift Pump House and Boundary Wall under Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/001406/2024-2025 | 25/BQA | 02/01/2025 | 03/10/2025 | ARIJIT GUHA | 14.44 | 0 | 0 | 0
Total | [13 empty] | 202.93 | 0 | 0