## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Ratanpur (Zone-B) Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block : Bankura-I ,Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000558/2023-2024 | 1994/BMD | 28/08/2023 | 26/12/2023 | UNITED TRADERS | 46.43 | 29.8 | 64.18 | 80
2 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000310/2023-2024 | 1956/BQA | 18/07/2023 | 16/02/2026 | SUBHADIP KOLEY | 110.17 | 69.22 | 62.83 | 100
3 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.86 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 26 Nos (Part- A) | Assistant Engineer | Junior Engineer | ORD/000295/2024-2025 | 652/BSD | 10/06/2024 | 03/01/2025 | PRADYUMNA KOLEY | 0.97 | 0.97 | 99.97 | 100
5 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 25 Nos (Part- B) | Assistant Engineer | Junior Engineer | ORD/000296/2024-2025 | 653/BSD | 10/06/2024 | 03/01/2025 | PRADYUMNA KOLEY | 0.94 | 0.94 | 99.99 | 100
6 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 25 Nos (Part- D) | Assistant Engineer | Junior Engineer | ORD/000298/2024-2025 | 655/BSD | 10/06/2024 | 03/01/2025 | PRADYUMNA KOLEY | 0.96 | 0.96 | 99.97 | 100
7 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 14 Nos (Part- F) | Assistant Engineer | Junior Engineer | ORD/000302/2024-2025 | 657/BSD | 10/06/2024 | 03/01/2025 | PRADYUMNA KOLEY | 0.65 | 0.65 | 99.98 | 100
8 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 25 Nos (Part- C) | Assistant Engineer | Junior Engineer | ORD/000297/2024-2025 | 654/BSD | 10/06/2024 | 03/01/2025 | PRADYUMNA KOLEY | 0.96 | 0.96 | 99.97 | 100
9 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 25 Nos (Part- E) | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 656/BSD | 10/06/2024 | 03/01/2025 | PRADYUMNA KOLEY | 0.96 | 0.96 | 99.99 | 100
10 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000278/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.86 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Construction of Low Lift Pump House and Boundary Wall under Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/001399/2024-2025 | 44/BQA | 02/01/2025 | 01/07/2026 | M/S KHAN ENTERPRISE | 28.99 | 0 | 0 | 1
12 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Sinking of 02 (Two) nos 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001389/2024-2025 | 36/BQA | 02/01/2025 | 12/01/2026 | SUBHADIP KOLE | 22.11 | 0 | 0 | 1
13 | BANKURA |  | Bankura Mechanical | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Submission of Application fee for Solar PV system of 8.04 Kwp at Ratanpur zone-B.Application no S000000862.SM/17287 |  |  | BILL/00708/2026-2027 |  | 07/08/2026 | 07/08/2026 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.05 | 0 | 0 | 0
Total | [13 empty] | 216.91 | 104.46 | 48.16