## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.86 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Ratanpur (Zone-B) Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block : Bankura-I ,Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000558/2023-2024 | 1994/BMD | 28/08/2023 | 26/12/2023 | UNITED TRADERS | 46.43 | 29.8 | 64.18 | 80
3 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 26 Nos (Part- A) | Assistant Engineer | Junior Engineer | ORD/000295/2024-2025 | 652/BSD | 10/06/2024 | 03/01/2025 | PRADYUMNA KOLEY | 0.97 | 0.97 | 99.97 | 100
4 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 25 Nos (Part- B) | Assistant Engineer | Junior Engineer | ORD/000296/2024-2025 | 653/BSD | 10/06/2024 | 03/01/2025 | PRADYUMNA KOLEY | 0.94 | 0.94 | 99.99 | 100
5 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 25 Nos (Part- D) | Assistant Engineer | Junior Engineer | ORD/000298/2024-2025 | 655/BSD | 10/06/2024 | 03/01/2025 | PRADYUMNA KOLEY | 0.96 | 0.96 | 99.97 | 100
6 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 14 Nos (Part- F) | Assistant Engineer | Junior Engineer | ORD/000302/2024-2025 | 657/BSD | 10/06/2024 | 03/01/2025 | PRADYUMNA KOLEY | 0.65 | 0.65 | 99.98 | 100
7 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 25 Nos (Part- C) | Assistant Engineer | Junior Engineer | ORD/000297/2024-2025 | 654/BSD | 10/06/2024 | 03/01/2025 | PRADYUMNA KOLEY | 0.96 | 0.96 | 99.97 | 100
8 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Creation of extra balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augumentation of Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) under Onda (BRGF Ph-I)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Onda, Name of OHR - Ratanpur and adjoining Mouzas Water Supply Scheme (Zone- B) (BRGF Ph-I), No. of Mouza :- 08 nos., Name of mouza:- Ratanpur (33), Bara Kurpa (34), Barkala (35), Machhrakhi (36), Chhota Kurpa (37), Pitambarpur (39), Benachapra (40), No. of Household- 25 Nos (Part- E) | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 656/BSD | 10/06/2024 | 03/01/2025 | PRADYUMNA KOLEY | 0.96 | 0.96 | 99.99 | 100
9 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000278/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.86 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). | SM/17287 | Augmentation | Construction of Low Lift Pump House and Boundary Wall under Augmentation works for Ratanpur and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/001399/2024-2025 | 44/BQA | 02/01/2025 | 01/07/2026 | M/S KHAN ENTERPRISE | 28.99 | 0 | 0 | 1
Total | [13 empty] | 84.59 | 35.24 | 41.67