## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000855/2023-2024 | 2955/BQA | 31/10/2023 | 30/11/2023 | MEASURE LAND | 4.5 | 0 | 0 | 95
2 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000188/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 4.8 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme |  |  | BILL/01657/2023-2024 | BP-2023-24-179 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.16 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Sinking of 3 Nos. 300 mm X 200 mm X 300 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 3 Nos. Pump Houses with ancillary works in different mouzas for Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000372/2023-2024 | 2034/BQA | 24/07/2023 | 02/04/2025 | PARAMESWAR CHOWDHURY | 237.05 | 0 | 0 | 30
5 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Formal work order for the work of Providing and Installation of High lift & Low lift pumping machineries and other electromehanical accessories for Augmentation of Simlapal piped water supply scheme for providing FHTC, Block - Simlapal Dist - Bankura under Bankura Mechanical Division, PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000451/2023-2024 | 1792/BMD | 01/08/2023 | 17/01/2026 | A.K.INDUSTRIES | 127.79 | 0 | 0 | 85
6 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of water supply scheme Dubrajpur Zone-B and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura. | Driller-in-Charge | Junior Engineer | ORD/000567/2023-2024 | 2025/BMD | 01/09/2023 | 24/08/2025 | SINHA ELECTRICALS | 71.68 | 0 | 0 | 66
7 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories in boosting site and existing pump house for Augmentation of water supply scheme Dubrajpur Zone-B and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Driller-in-Charge | Junior Engineer | ORD/000146/2024-2025 | 489/BMD | 09/07/2024 | 04/07/2025 | PRADIP KUMAR DHABAL | 25.33 | 0 | 0 | 20
8 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Gaseous Chlorination System for Augmentation of Dubrajpur Zone-B water supply scheme under Dubrajpur water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000266/2024-2025 | 774/BMD | 20/08/2024 | 29/03/2026 | GOENKA ENTERPRISE | 40.86 | 0 | 0 | 90
9 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Laying of HDPE pipeline, Sinking of 1 No. 300 mm X 200 mm X 250 Metre deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe, Construction of Valve Chamber, Construction of Boundary wall at Tubewell site, Construction of Pump House for Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000061/2024-2025 | 1486/BQA | 18/06/2024 | 02/12/2025 | SUBHENDU SEKHAR GORAI | 96.46 | 0 | 0 | 85
10 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Sinking of 3 Nos. 300 mm X 200 mm X 240 m deep Tubewell (Replacement Tubewell) by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Repairing and painting of Over Head Reservoir (Capacity 700 Cum., staging height 20 Mtr.), Pump House, Operator Room, Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Dubrajpur, Zone-B water Supply Scheme under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001975/2024-2025 | 669/BQA | 12/03/2025 | 11/05/2025 | S B ASSOCIATES | 78.15 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Sinking of 3 Nos. 300 mm X 200 mm X 300 m deep Tubewell (Replacement) by Rig boring method including interconnection with 100 mm dia. G.I. Pipe for Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000612/2022-2023 | 570/BQA | 17/03/2023 | 16/04/2023 | SUBHADIP KOLEY | 66.27 | 0 | 0 | 65
Total | [13 empty] | 763.05 | 0 | 0