## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000855/2023-2024 | 2955/BQA | 31/10/2023 | 30/11/2023 | MEASURE LAND | 4.5 | 4.44 | 98.63 | 95
2 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000188/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 4.8 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme |  |  | BILL/01657/2023-2024 | BP-2023-24-179 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.16 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Sinking of 3 Nos. 300 mm X 200 mm X 300 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 3 Nos. Pump Houses with ancillary works in different mouzas for Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000372/2023-2024 | 2034/BQA | 24/07/2023 | 02/04/2025 | PARAMESWAR CHOWDHURY | 237.05 | 37.92 | 16 | 30
5 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Formal work order for the work of Providing and Installation of High lift & Low lift pumping machineries and other electromehanical accessories for Augmentation of Simlapal piped water supply scheme for providing FHTC, Block - Simlapal Dist - Bankura under Bankura Mechanical Division, PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000451/2023-2024 | 1792/BMD | 01/08/2023 | 17/01/2026 | A.K.INDUSTRIES | 127.79 | 19.91 | 15.58 | 85
6 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of water supply scheme Dubrajpur Zone-B and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura. | Driller-in-Charge | Junior Engineer | ORD/000567/2023-2024 | 2025/BMD | 01/09/2023 | 24/08/2025 | SINHA ELECTRICALS | 71.68 | 47.77 | 66.65 | 66
7 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories in boosting site and existing pump house for Augmentation of water supply scheme Dubrajpur Zone-B and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Driller-in-Charge | Junior Engineer | ORD/000146/2024-2025 | 489/BMD | 09/07/2024 | 04/07/2025 | PRADIP KUMAR DHABAL | 25.33 | 0 | 0 | 20
8 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Sinking of 3 Nos. 300 mm X 200 mm X 300 m deep Tubewell (Replacement) by Rig boring method including interconnection with 100 mm dia. G.I. Pipe for Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000612/2022-2023 | 570/BQA | 17/03/2023 | 16/04/2023 | SUBHADIP KOLEY | 66.27 | 60.47 | 91.25 | 65
9 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Work Order for Installation of scheme information board for 6 nos. site of Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) [SM/17288] within Simlapal Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001926/2024-2025 | 170\KSD | 07/03/2025 | 17/03/2025 | SUBHADIP KOLE | 0.9 | 0 | 0 | 90
10 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/17288 | Augmentation | Work Order for Installation of scheme information board for 4 nos. site of Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) [SM/17288] and 2 nos. site of Augmentation of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) [SM/18894] within Simlapal Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001927/2024-2025 | 171\KSD | 07/03/2025 | 17/03/2025 | PRADYUMNA KOLEY | 0.9 | 0 | 0 | 90
Total | [13 empty] | 549.39 | 170.52 | 31.04