## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme (Phase- I). | SM/17291 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 11.54 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme (Phase- I). | SM/17291 | Augmentation | Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme (Phase- I). |  |  | BILL/00192/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme (Phase- I). | SM/17291 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for Augmentation of Bikna and its adjoining mouzas piped water supply scheme (JJM Revision) Block-Bankura-II Dist -Bankura under Bankura Mechanical Division PHE Dte | Assistant Engineer | Junior Engineer | ORD/000559/2023-2024 | 1995/BMD | 28/08/2023 | 26/12/2023 | M/S NABIN GOPAL SENGUPTA | 63.49 | 0 | 0 | 67
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme (Phase- I). | SM/17291 | Augmentation | New Service connection at Domanbandi for augmenrtation of Bikna water supply scheme (SM/17291) under BMD PHE Dte. |  |  | BILL/00952/2024-2025 | BP-2024-25-233 | 27/09/2024 | 27/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.07 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme (Phase- I). | SM/17291 | Augmentation | Retrofitting works for creation of Balance 'FHTC (Functional House Hold Tap Connection') & paralal pipe line of existing 'FHTC in connection with Jal Jeevan Mission (JJM) for Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura -II, Name of OHR - Bikna Water Supply Scheme, No. of Mouza :-03 nos. Name of mouza:- Bikna (235), Kuraria (254), Katnar (255), No. of Household- 340 nos. | Assistant Engineer | Junior Engineer | ORD/000816/2022-2023 | 718/BQA | 30/03/2023 | 01/07/2025 | JAGADISH BANERJEE | 40.96 | 0 | 0 | 51
6 | BANKURA |  | Bankura Division | Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme (Phase- I). | SM/17291 | Augmentation | Creation of Platfrom of Existing 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura -II, Name of OHR - Bikna Water Supply Scheme, No. of Mouza :- 03 nos.Name of mouza:- Bikna (235), Kuraria (254), Katnar (255), No. of Household- 1363 nos. | Assistant Engineer | Junior Engineer | ORD/000041/2023-2024 | 872/BQA | 18/04/2023 | 13/10/2025 | GON ASSOCIATES | 25.37 | 0 | 0 | 76
Total | [13 empty] | 144.93 | 0 | 0