## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17292 | Augmentation | Sinking of 2 (Two) Nos. 200 mm dia. X 5.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000341/2023-2024 | 1965/BQA | 18/07/2023 | 13/04/2024 | I.R.CONSTRUCTION | 141.73 | 0 | 0 | 30
2 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17292 | Augmentation | Laying of HDPE pipeline, Construction of Valve Chamber for Augmentation of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000162/2024-2025 | 1827/BQA | 12/07/2024 | 10/10/2024 | M/S TARUN KUMAR PATRA | 28.3 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17292 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of illumination arrangement , installation of new charger panel , construction of neutralization pit , supply of XLPE cables , chlorinator items for Augmentation of Belatikari Zone-B water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000164/2024-2025 | 506/BMD | 09/07/2024 | 06/11/2024 | M/S SAJAHAN CHOWDHURY | 22.11 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17292 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000076/2024-2025 | 1493/BQA | 18/06/2024 | 18/07/2024 | MESAURE LAND | 1.89 | 0 | 0 | 90
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17292 | Augmentation | Acceptance cum Formal work order for the work of Additional Work for Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. under Bankura Mechanical Division, P.H.E. Dte | Driller-in-Charge | Junior Engineer | ORD/000316/2024-2025 | 857/BMD | 29/08/2024 | 28/10/2024 | M.S. ENTERPRISE | 1.18 | 0 | 0 | 100
6 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17292 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000181/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 2.77 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17292 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Belatikri Zone-B water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000570/2023-2024 | 2027/BMD | 01/09/2023 | 03/03/2026 | M.S. ENTERPRISE | 83.1 | 0 | 0 | 77
8 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17292 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of submersible pumping machineries for Augmentation for Belatikri Zone-B water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Driller-in-Charge | Junior Engineer | ORD/000138/2024-2025 | 444/BMD | 27/06/2024 | 21/02/2026 | M.S. ENTERPRISE | 16.65 | 0 | 0 | 89
9 | BANKURA |  | Bankura Division | Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17292 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 450 Cum., staging height 20 Mtr.), Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000132/2025-2026 | 1293/BQA | 17/06/2025 | 18/12/2025 | TAPAS KUMAR HAZRA | 14.1 | 0 | 0 | 0
10 | BANKURA |  | Bankura Mechanical | Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17292 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System & construction of one no RBTW with other allied work at Belatikari water supply scheme under Sarenga Block under BMD PHE Dte | Assistant Engineer | Junior Engineer | ORD/000194/2025-2026 | 639/BMD | 11/07/2025 | 09/10/2025 | DEBJYOTI BASU | 19.49 | 0 | 0 | 0
Total | [13 empty] | 331.33 | 0 | 0