## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Baricha, Zone-A and its adjoining Mouzas under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17295 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of illumination arrangement for Augmentation for Baricha Zone -A water supply scheme under Baricha water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000331/2024-2025 | 868/BMD | 29/08/2024 | 27/12/2024 | M/S TARUN KUMAR PATRA | 4.84 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-A and its adjoining Mouzas under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17295 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Baricha, Zone-A and its adjoining Mouzas under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000830/2023-2024 | 2956/BQA | 31/10/2023 | 30/11/2023 | GEO SOLUTION | 3.28 | 3.21 | 97.77 | 97
3 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-A and its adjoining Mouzas under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17295 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000185/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 3.45 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-A and its adjoining Mouzas under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17295 | Augmentation | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Baricha, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000406/2023-2024 | 2091/BQA | 27/07/2023 | 02/04/2025 | PARAMESWAR CHOWDHURY | 197.38 | 45.89 | 23.25 | 27
5 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Baricha, Zone-A and its adjoining Mouzas under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17295 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation for Boricha Zone-A and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000572/2023-2024 | 2028/BMD | 01/09/2023 | 30/12/2023 | S.P. CONSTRUCTION | 96.37 | 78.56 | 81.51 | 80
Total | [13 empty] | 305.32 | 127.66 | 41.81