## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. | SM/17297 | Augmentation | Sinking of 2 Nos. 300 mm X 200 mm X 300 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe, Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿, Construction of High Lift Pump House and 200 Cum. CWR with Collecting Line ancillary works in different mouzas for Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000322/2023-2024 | 1926/BQA | 13/07/2023 | 08/04/2024 | SIB SANKAR CHOWDHURY | 257.41 | 29.81 | 11.58 | 23
2 | BANKURA |  | Bankura Division | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. | SM/17297 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000836/2023-2024 | 2962/BQA | 31/10/2023 | 30/11/2023 | MEASURE LAND | 2.4 | 2.34 | 97.69 | 97
3 | BANKURA |  | Bankura Mechanical | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. | SM/17297 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation of Dhanara and its adjoining mouzas water supply scheme under Jal Jeeven mission Progremme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000989/2023-2024 | 2849/BMD | 09/02/2024 | 28/07/2026 | DEY ENTERPRISE | 144.45 | 0 | 0 | 21
4 | BANKURA |  | Bankura Division | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. | SM/17297 | Augmentation | Laying of HDPE pipeline, Construction of Valve Chamber and Construction of Boundary wall at CWR site & Tubewell site for Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000163/2024-2025 | 1828/BQA | 12/07/2024 | 02/04/2025 | D. S. ENTERPRISE | 47.76 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. | SM/17297 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Submersible pumping machineries and other electromechanical accessories for Augmentation works at T/W No-II at Katalda Pump house under Dhanara Water supply scheme and its Adjoing moujazs water supply scheme under Jal Jeevan Mission progremme,Under Raipur Block under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000262/2024-2025 | 517/BMD | 09/07/2024 | 06/11/2024 | R.K. ENTERPRISE | 7.09 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. | SM/17297 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000189/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 3.7 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. | SM/17297 | Augmentation | quotation Bill for New Pump house no.1 at Katalda under Danara w/s scheme augmentation work (SM/17297) |  |  | BILL/00946/2024-2025 | BP-2024-25-231 | 27/09/2024 | 27/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.3 | 0 | 0 | 0
8 | BANKURA |  | Bankura Mechanical | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. | SM/17297 | Augmentation | Quotation Bill for New Pump house no.2 at Katalda under Danara w/s scheme augmentation work (SM/17297) |  |  | BILL/00947/2024-2025 | BP-2024-25-232 | 27/09/2024 | 27/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.58 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. | SM/17297 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 400 Cum., staging height 20 Mtr.), CWR, Pump House cum Chlorine Room and Construction of Boundary Wall and Guard Room with all allied works of Augmentation works for Dhanara and Its Adjoining mouzas Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001980/2024-2025 | 674/BQA | 12/03/2025 | 10/06/2025 | SINGHA ENTERPRISE | 51.93 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. | SM/17297 | Augmentation | Sinking of 2 (Two) Nos. 200 mm dia. X 5.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm MS collecting line from river bed tube well to CWR with allied works for Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division in Bankura District, P.H.E. Dte. | Assistant Engineer |  | ORD/000718/2025-2026 | 2287/BQA | 27/11/2025 | 26/01/2026 | SIBSANKAR CHOWDHURY | 23.88 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. | SM/17297 | Augmentation | Work Order for Installation of scheme information board for 4 nos. site of Augmentation of Dhanara Water Supply Scheme (SM/17297) and 2 nos. site of Retrofitting of Lurka (Zone-VA) Water Supply Scheme (BRGF Ph-I) (SM/16940) within Raipur Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001932/2024-2025 | 175\KSD | 07/03/2025 | 17/03/2025 | SANDHYA DEY | 0.9 | 0 | 0 | 90
12 | BANKURA |  | Bankura Division | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. | SM/17297 | Augmentation | Repair and Maintenance work of the Road trom Dublala to Thakurabara under Raipur Block in the District of Bankura ,Vide Package No- WB-03-ADB-08, Road Length-2.685 Km. ( Augmentation of Dhanara & its adjoining mouzas of water supply scheme) |  |  | BILL/01461/2024-2025 | BP/483/2024-25 | 22/03/2025 | 22/03/2025 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 2.36 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Augmentation Works for Dhanara and its Adjoining mouza Water Supply Scheme under Jal Jeevan Mission Programme. | SM/17297 | Augmentation | Repair and Maintenance work of the Road from Sahajpur to Moulasol under Raipur Block in the Distiict of Bankura ,Vide Package No WB-03-44, Road Length-9.96 Km. ( Augmentation of Dhanara & its adjoining mouzas of water supply scheme) |  |  | BILL/01464/2024-2025 | BP/483/2024-25 | 22/03/2025 | 22/03/2025 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 3.15 | 0 | 0 | 0
Total | [13 empty] | 548.9 | 32.15 | 5.86