## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Sub-Surface water based water supply scheme (Left out from BRGF Mouza) for Onda. | SM/17301 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Sub Surface water based water supply scheme(Left outfrom BRGF Mouza) for Onda under onda block under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer |  | ORD/000543/2023-2024 | 1979/BMD | 28/08/2023 | 26/12/2023 | UNITED TRADERS | 56.54 | 31.01 | 54.84 | 55
2 | BANKURA |  | Bankura Mechanical | Augmentation of Sub-Surface water based water supply scheme (Left out from BRGF Mouza) for Onda. | SM/17301 | Augmentation | Acceptance cum Formal work order for the work of Providing of drilling materials for sinking of RBTW for rejuvenation of Onda water supply Scheme connection to JJM Program Block: Onda in the district of Bankura under Bankura Mechanical Division P.H.E Dte | Assistant Engineer |  | ORD/000210/2022-2023 | 1346/BMD | 11/11/2022 | 11/12/2022 | ALPHA ENTERPRISE | 23.3 | 23.19 | 99.5 | 0
3 | BANKURA |  | Bankura Division | Augmentation of Sub-Surface water based water supply scheme (Left out from BRGF Mouza) for Onda. | SM/17301 | Augmentation | PAYMENT TO RAIL |  |  | BILL/00006/2023-2024 | FHTC/20 | 20/04/2023 | 20/04/2023 | SOUTH EASTERN RAILWAY | 6.3 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Sub-Surface water based water supply scheme (Left out from BRGF Mouza) for Onda. | SM/17301 | Augmentation | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of Sub-Surface water based water supply scheme (Left out from BRGF Mouza) for Onda under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000471/2023-2024 | 2326/BQA | 14/08/2023 | 01/04/2026 | GOPAL CHANDRA CHOWDHURY | 655.34 | 518.15 | 79.07 | 56
5 | BANKURA |  | Bankura Division | Augmentation of Sub-Surface water based water supply scheme (Left out from BRGF Mouza) for Onda. | SM/17301 | Augmentation | Construction of Boundary Wall at Onda (Zone - II) H/W Site in connection with Jal Jeevan Mission (JJM) for Augmentation of Onda Water Supply Scheme within Onda Block under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Total Length:- 300 Mtr.) | Assistant Engineer | Junior Engineer | ORD/000213/2024-2025 | 1864/BQA | 12/07/2024 | 01/10/2025 | SUBHAM CONSTRUCTION | 35.29 | 0 | 0 | 5
Total | [13 empty] | 776.78 | 572.35 | 73.68