## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 60.93 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Augmentation works for Kadra (Zone- G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) |  |  | BILL/00218/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 30/12/2023 | K S GROUP | 5.18 | 0 | 0 | 70
4 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other allied electro-mechanical accessories for Augmentation for KULDIHI piped water supply scheme (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Sarenga , Dist: Bankura | Driller-in-Charge | Junior Engineer | ORD/000135/2024-2025 | 441/BMD | 27/06/2024 | 31/12/2024 | ABHIJIT MUKHERJEE | 19.59 | 4.57 | 23.33 | 65
5 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Gaseous Chlorination System for Augmentation of Kuldihi water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Driller-in-Charge | Junior Engineer | ORD/001094/2023-2024 | 3069/BMD | 12/03/2024 | 10/07/2024 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 41.85 | 36.21 | 86.51 | 70
6 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with making MS Tee and ancillary works at Baraamjhor village due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000638/2023-2024 | 2580/BQA | 15/09/2023 | 15/10/2023 | SANJOY PATRA | 4.02 | 4 | 99.46 | 50
7 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000835/2023-2024 | 2961/BQA | 31/10/2023 | 30/11/2023 | GEO SOLUTION | 4.45 | 4.45 | 99.95 | 96
8 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Sinking of 3 Nos. 300 mm X 200 mm X 200 Metre deep Tubewell (Replacement) by Rig boring method including interconnection with 100 mm dia. G.I. Pipe for Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001298/2023-2024 | 809/BQA | 07/03/2024 | 21/04/2024 | ANJAN INFRASTUCTURE PVT LTD. | 50.34 | 46.56 | 92.48 | 98
9 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | New service connection charges for Kuldihi, Application No- 2004835893 |  |  | BILL/00701/2024-2025 | BP-2024-25-164 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.31 | 0 | 0 | 0
10 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | New service connection for Kuldiha water supply scheme under Bankura Mechanical Division PHE Dte. |  |  | BILL/00122/2024-2025 | BP-2024-25-13 | 10/05/2024 | 10/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.23 | 0 | 0 | 0
11 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | New Service Connection for Kuldihi , Application No- 2004835760 |  |  | BILL/00702/2024-2025 | BP-2024-25-165 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0 | 0
12 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | New service connection for Kuldiha water supply scheme under Bankura Mechanical Division PHE Dte. |  |  | BILL/00029/2024-2025 | BP-2024-25-12 | 10/05/2024 | 10/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0 | 0
13 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | New 3 phase connection for Kuldihi W/S (Scheme) Telijant site |  |  | BILL/00950/2024-2025 | BP-2024-25-230 | 27/09/2024 | 27/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.16 | 0 | 0 | 0
14 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | New Service connection charge of WBSEDCL Kuldiha |  |  | BILL/00703/2024-2025 | BP-2024-25-166 | 06/08/2024 | 06/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.23 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Sinking 3 Nos 300x200 Rig Bore Tubewell, Construction of 250 Cum OHR, 3 Nos. Pump House, Boundary Wall, Rising Main and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000475/2023-2024 | 2330/BQA | 14/08/2023 | 02/07/2025 | PRINCE INDUTRIES (INDIA) | 566.03 | 428.61 | 75.72 | 82
16 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000077/2024-2025 | 1497/BQA | 18/06/2024 | 01/04/2025 | SWAPAN KUMAR CHANDRA | 17.8 | 0 | 0 | 90
17 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Work Order for Installation of scheme information board for 6 nos. Pump House site of Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) [SM/17302] within Sarenga Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001921/2024-2025 | 165\KSD | 07/03/2025 | 17/03/2025 | SUBHADIP KOLE | 0.9 | 0 | 0 | 90
18 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Work Order for Installation of scheme information board for 2 nos. OHR and 4 nos. Pump House site of Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) [SM/17302] within Sarenga Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001920/2024-2025 | 164\KSD | 07/03/2025 | 17/03/2025 | PRADYUMNA KOLEY | 0.9 | 0 | 0 | 90
19 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Work Order for Installation of scheme information board for 1 no. site of Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) [SM/17302], 3 nos. site of Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) [SM/17438] and 1 no. site Proposed Ground Water Based Bansi Pipe Water Supply Scheme [SM/18038] within Sarenga Block and 1 no. site of Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal water Supply Scheme (BRGF Ph-I) [SM/17434] under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001922/2024-2025 | 166\KSD | 07/03/2025 | 17/03/2025 | SUBHADIP KOLE | 0.9 | 0 | 0 | 90
20 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Supply of sluice valve, construction of valve chamber and MS pipeline work for distribution main of Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000180/2025-2026 | 1316/BQA | 17/06/2025 | 16/08/2025 | PRINCE INDUSTRIES (INDIA) | 7.66 | 0 | 0 | 95
21 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Kuldiha & its adjoining mouzas under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000568/2023-2024 | 2034/BMD | 01/09/2023 | 29/06/2028 | A.K.INDUSTRIES | 72.58 | 54 | 74.4 | 66
22 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17302 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 700 Cum., staging height 20 Mtr.), Pump House, Operator Room, Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Kuldiha water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001977/2024-2025 | 671/BQA | 12/03/2025 | 10/06/2025 | AJIT KUMAR PAUL | 23.77 | 0 | 0 | 90
Total | [13 empty] | 903.84 | 578.4 | 63.99