## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Beliatore & its adjoining mouzas Water Supply Scheme (Phase- I). | SM/17303 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000119/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.11 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Beliatore & its adjoining mouzas Water Supply Scheme (Phase- I). | SM/17303 | Augmentation | Augmentation works for Beliatore & its adjoining mouzas Water Supply Scheme (Phase- I). |  |  | BILL/00193/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Beliatore & its adjoining mouzas Water Supply Scheme (Phase- I). | SM/17303 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000275/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.11 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Beliatore & its adjoining mouzas Water Supply Scheme (Phase- I). | SM/17303 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro-mechanical accessories for Augmentation of Beliatore and adjoining mouzas (Phase-I) under Bankura Mechanical Division PHE Dte Block- Barjora Dist -Bankura | Assistant Engineer | Junior Engineer | ORD/000574/2023-2024 | 2036/BMD | 01/09/2023 | 03/04/2025 | M/S BIPUL BANERJEE | 45.43 | 20.43 | 44.97 | 45
5 | BANKURA |  | Bankura Division | Augmentation works for Beliatore & its adjoining mouzas Water Supply Scheme (Phase- I). | SM/17303 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Beliatore & its adjoining mouzas Water Supply Scheme (Phase- I). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001189/2023-2024 | 441/BQA | 08/02/2024 | 09/03/2024 | LEMNISCATE | 2 | 0 | 0 | 100
Total | [13 empty] | 53.14 | 20.43 | 38.44