## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17304 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-E (Naria) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000604/2022-2023 | 557/BQA | 17/03/2023 | 01/05/2023 | ASHOKE KUMAR DEY | 72.75 | 72.72 | 99.96 | 55
2 | BANKURA |  | Bankura Division | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17304 | Augmentation | Work Order for Extension of UPVC pipeline at Debedia village under Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer |  | ORD/000454/2023-2024 | 262/KSD | 24/08/2023 | 08/09/2023 | S. S. S. ENTERPRISES | 0.6 | 0.6 | 99.5 | 25
3 | BANKURA |  | Bankura Division | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17304 | Augmentation | Work Order for Extension of UPVC pipeline at Debedia village under Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer |  | ORD/000452/2023-2024 | 260/KSD | 24/08/2023 | 08/09/2023 | S. S. S. ENTERPRISES | 0.74 | 0.74 | 99.38 | 25
4 | BANKURA |  | Bankura Division | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17304 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000166/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 2.59 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17304 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Naria (Zone E) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Driller-in-Charge | Junior Engineer | ORD/000056/2025-2026 | 252/BMD | 14/05/2025 | 12/08/2025 | WEST BENGAL ENGINEERING CO. | 28.18 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17304 | Augmentation | Laying HDPE pipeline from Dighi to Dhajamanipur and at Brahmadanga village to increase pressure at Dhajamanipur and Brahmadanga village in connection with Augmentation of Naria (Zone-E) Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000339/2024-2025 | 2304/BQA | 04/09/2024 | 02/01/2026 | MANAS DEY | 7.44 | 0 | 0 | 90
7 | BANKURA |  | Bankura Division | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17304 | Augmentation | Laying pipeline, providing FHTC (Functional House Hold Tap Connection) with all allied works of Zone-E (Naria) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001785/2024-2025 | 496/BQA | 25/02/2025 | 26/04/2025 | ID MOHAMMAD MANDAL | 2.2 | 0 | 0 | 90
Total | [13 empty] | 114.5 | 74.06 | 64.68