## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Infrastructure development for Taldangra Sub-District water Testing Laboratory regarding NABL accreditation under Bankura Division, PHE Dte. related to support activities under JJM | SM/17416 | Support-WQMSP | WORKS FOR EXTENSION OF TALDANGRA SUB - DISTRICT LABORATORY UNDER BANKURA RWS SUB-DIVISION AT TALDANGRA BLOCK CAMPASS 2021 - 22 | Assistant Engineer | Junior Engineer | ORD/000012/2023-2024 | 761/BQA | 04/04/2023 | 30/06/2024 | UTTAM KUMAR SINHAMAHAPATRA | 16.79 | 16.56 | 98.64 | 98
Total | [13 empty] | 16.79 | 16.56 | 98.64