## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Betanal Zone-B Water Supply Scheme | SM/17418 | Augmentation | Augmentation of Betanal Zone-B Water Supply Scheme |  |  | BILL/00179/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Betanal Zone-B Water Supply Scheme | SM/17418 | Augmentation | Augmentation of Betanal Zone-B Water Supply Scheme |  |  | BILL/01617/2023-2024 | BP-2023-24-154 | 19/03/2024 | 19/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.74 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Betanal Zone-B Water Supply Scheme | SM/17418 | Augmentation | Augmentation of Betanal Zone-B Water Supply Scheme |  |  | BILL/01627/2023-2024 | BP-2023-24-155 | 19/03/2024 | 19/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.28 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Betanal Zone-B Water Supply Scheme | SM/17418 | Augmentation | Load enhancement work for Betanal Zone-B water supply scheme at Indus Block Under B.M.D P.H.E Dte |  |  | BILL/00006/2024-2025 | BP-2024-25-92 | 11/06/2024 | 11/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.47 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Betanal Zone-B Water Supply Scheme | SM/17418 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF BETANAL ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000326/2023-2024 | 1930/BQA | 13/07/2023 | 07/01/2026 | SINGHA ENTERPRISE | 197.87 | 0 | 0 | 50
6 | BANKURA |  | Bankura Mechanical | Augmentation of Betanal Zone-B Water Supply Scheme | SM/17418 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Betanal Zone-B piped water supply scheme(BRGF Ph-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000366/2023-2024 | 1698/BMD | 28/07/2023 | 12/09/2025 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 67.31 | 34.66 | 51.49 | 40
7 | BANKURA |  | Bankura Mechanical | Augmentation of Betanal Zone-B Water Supply Scheme | SM/17418 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of MCC Panel and other electromechanical acessories at boosting P.H for Augmentation of Betanal Zone-B Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000317/2024-2025 | 858/BMD | 29/08/2024 | 25/06/2025 | M/S SAJAHAN CHOWDHURY | 18.51 | 0 | 0 | 0
8 | BANKURA |  | Bankura Mechanical | Augmentation of Betanal Zone-B Water Supply Scheme | SM/17418 | Augmentation | Acceptance cum Formal work order for the work of Augmentation of sub- station equipment at Betanal Zone-B piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 859/BMD | 29/08/2024 | 27/12/2024 | M.S. ENTERPRISE | 15.51 | 0 | 0 | 100
9 | BANKURA |  | Bankura Division | Augmentation of Betanal Zone-B Water Supply Scheme | SM/17418 | Augmentation | Instalation of scheme information board for 2 nos. sites of Augmentation of Betanal Zone-A Water Supply Scheme (SM/17692) & Augmentation of Betanal Zone-B Water Supply Scheme (SM/17418), 1 no. site of Augmentation of Karisunda Water Supply Scheme (SM/17419), 2 nos. sites of Augmentation of Kushmuri Zone-A Water Supply Scheme (SM/17420 ) & Augmentation of Kushmuri Zone-B Water Supply Scheme within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001814/2024-2025 | 540/VSD | 27/09/2024 | 12/10/2024 | PARTHA ROY | 0.75 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation of Betanal Zone-B Water Supply Scheme | SM/17418 | Augmentation | Construction of Boundary Wall and Pump House for Augmentation of Betanal (Zone-B) Piped Water Supply Scheme. | Assistant Engineer |  | ORD/001351/2024-2025 | 3168/BQA | 24/12/2024 | 19/09/2025 | ASEK ALI KHAN | 12.96 | 0 | 0 | 80
Total | [13 empty] | 321.89 | 34.66 | 10.77