## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Karisunda Water Supply Scheme | SM/17419 | Augmentation | Augmentation of Karisunda Water Supply Scheme |  |  | BILL/00189/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Karisunda Water Supply Scheme | SM/17419 | Augmentation | Augmentation of Karisunda Water Supply Scheme |  |  | BILL/01620/2023-2024 | BP-2023-24-153 | 19/03/2024 | 19/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.19 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Karisunda Water Supply Scheme | SM/17419 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Karisunda piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000384/2023-2024 | 1707/BMD | 28/07/2023 | 28/03/2024 | ABHIJIT MUKHERJEE | 61.17 | 0 | 0 | 66
4 | BANKURA |  | Bankura Division | Augmentation of Karisunda Water Supply Scheme | SM/17419 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF KARISUNDA PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000391/2023-2024 | 2051/BQA | 24/07/2023 | 02/04/2025 | SIB SANKAR CHOWDHURY | 177.69 | 0 | 0 | 65
5 | BANKURA |  | Bankura Division | Augmentation of Karisunda Water Supply Scheme | SM/17419 | Augmentation | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.4 m x 3.6 m) at 3rd TW site at mouza Karisunda (J.L No-54, Plot No-1887) for Karisunda Water Supply Scheme (BRGF) wihin Indas block under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer |  | ORD/001386/2024-2025 | 33/BQA | 02/01/2025 | 02/04/2025 | BIDHAN BANERJEE | 6.58 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation of Karisunda Water Supply Scheme | SM/17419 | Augmentation | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.4 m x 3.6 m) at 4th TW site at mouza Belbandhi (J.L No-22, Plot No-8) for Karisunda Water Supply Scheme (BRGF) wihin Indas block under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001385/2024-2025 | 31/BQA | 02/01/2025 | 02/04/2025 | SK FAZLUL ALAM | 6.57 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation of Karisunda Water Supply Scheme | SM/17419 | Augmentation | Construction of boundary wall approx 60 mtr long of Karisunda water supply scheme (BRGF) (3rd T/W Site) at mouza Karisunda (J.L No-54, Plot No-1887) in Indas Block under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001384/2024-2025 | 75/BQA | 06/01/2025 | 01/02/2026 | M/S. RAJU SINGH | 4.42 | 0 | 0 | 0
Total | [13 empty] | 263.13 | 0 | 0