## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Kushmuri Zone-A Water Supply Scheme | SM/17420 | Augmentation | Construction of 2nos. boundary wall approx 60 mtr long for Kushmuri Zone- A water supply scheme in Indas Block under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000681/2023-2024 | 2630/BQA | 21/09/2023 | 19/03/2024 | ANNDAMAYEE CONSTRUCTION | 8.86 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Kushmuri Zone-A Water Supply Scheme | SM/17420 | Augmentation | Augmentation of Kushmuri Zone-A Water Supply Scheme |  |  | BILL/00176/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation of Kushmuri Zone-A Water Supply Scheme | SM/17420 | Augmentation | Construction of Boundary Wall and Pump House for Augmentation of Kushmuri (Zone-A) Piped Water Supply Scheme. | Assistant Engineer |  | ORD/001357/2024-2025 | 3178/BQA | 24/12/2024 | 24/03/2025 | BIJOY KOLEY | 12.97 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Kushmuri Zone-A Water Supply Scheme | SM/17420 | Augmentation | Laying distribution system for Kushmuri Zone- A W/S Scheme (BRGF Phase-I) within Indas Block in connection with Jal Jeevan Mission (JJM) under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000678/2023-2024 | 2628/BQA | 21/09/2023 | 30/04/2024 | MAYA CONSTRUCTION | 10.92 | 9.09 | 83.25 | 15
5 | BANKURA |  | Bankura Mechanical | Augmentation of Kushmuri Zone-A Water Supply Scheme | SM/17420 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kushmuri (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000370/2023-2024 | 1700/BMD | 28/07/2023 | 04/01/2026 | TAPAN KUMAR SARKAR | 59.31 | 31.25 | 52.69 | 53
6 | BANKURA |  | Bankura Division | Augmentation of Kushmuri Zone-A Water Supply Scheme | SM/17420 | Augmentation | Construction of 2 nos. Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.0 m x 4.0 m) for Kushmuri Zone- A Water Supply Scheme wihin Indas block under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000679/2023-2024 | 2629/BQA | 21/09/2023 | 27/03/2025 | SAYED PAHALOWAN | 13.23 | 0 | 0 | 30
7 | BANKURA |  | Bankura Division | Augmentation of Kushmuri Zone-A Water Supply Scheme | SM/17420 | Augmentation | Creation of 'FHTC (Funtional House Hold Tap Connection)' for extra house hold in connection with Jal Jeevan Mission (JJM) of Kushmuri Zone- A W/S Scheme (BRGF Phase-I) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. Block Name:- Indas, Location of OHR :- Gobindapur, No. of Mouzas Covered :- 5 nos., Name of Mouzas & JL No.:- Sanpura (57), Jagaldwip (58), Dasaratbati (61), Bhabapur (100), Kushmuri (98) Total No. House Hold:- 55 | Assistant Engineer | Junior Engineer | ORD/000759/2023-2024 | 2865/BQA | 11/10/2023 | 25/11/2023 | MOHAN KUMAR ROY | 28.65 | 25.24 | 88.11 | 45
8 | BANKURA |  | Bankura Division | Augmentation of Kushmuri Zone-A Water Supply Scheme | SM/17420 | Augmentation | Creation of 'FHTC (Funtional House Hold Tap Connection)' for extra house hold in connection with Jal Jeevan Mission (JJM) of Kushmuri Zone- A W/S Scheme (BRGF Phase-I) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. Block Name:- Indas, Location of OHR :- Gobindapur, No. of Mouzas Covered :- 5 nos., Name of Mouzas & JL No.:- Sanpura (57), Jagaldwip (58), Dasaratbati (61), Bhabapur (100), Kushmuri (98) Total No. House Hold:- 55 | Assistant Engineer | Junior Engineer | ORD/000757/2023-2024 | 2864/BQA | 11/10/2023 | 01/04/2025 | GOURANGA NANDI | 28.65 | 20.69 | 72.2 | 95
9 | BANKURA |  | Bankura Mechanical | Augmentation of Kushmuri Zone-A Water Supply Scheme | SM/17420 | Augmentation | Acceptance cum Formal work order for the work of Augmentation of sub- station equipment at Kushmuri (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 776/BMD | 20/08/2024 | 18/12/2024 | M.S. ENTERPRISE | 14.05 | 0 | 0 | 100
10 | BANKURA |  | Bankura Mechanical | Augmentation of Kushmuri Zone-A Water Supply Scheme | SM/17420 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at Kushmuri CWR site under Kushmuri zone-A piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Indus, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000123/2024-2025 | 1071/BMSD | 05/07/2024 | 16/07/2025 | UNICON | 4.38 | 0 | 0 | 100
Total | [13 empty] | 182.53 | 86.27 | 47.26