## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Sashpur Zone-B Water Supply Scheme | SM/17421 | Augmentation | Augmentation of Sashpur Zone-B Water Supply Scheme |  |  | BILL/00175/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Sashpur Zone-B Water Supply Scheme | SM/17421 | Augmentation | New Service connection for Ashwinpur Boosting Tw Site of Sashpur Zone B water supply scheme under B.M.D PHE Dte.(SM/17421) |  |  | BILL/01136/2024-2025 | BP-2024-25-283 | 19/11/2024 | 19/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.07 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Sashpur Zone-B Water Supply Scheme | SM/17421 | Augmentation | Augmentation of Sashpur Zone-B Water Supply Scheme |  |  | BILL/01618/2023-2024 | BP-2023-24-152 | 19/03/2024 | 19/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.52 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Sashpur Zone-B Water Supply Scheme | SM/17421 | Augmentation | Load Enhancement charges for SASPUR ZONE-B Water supply scheme under Bankura Mechanical Division PHE DTE |  |  | BILL/00721/2024-2025 | BP-2024-25-198 | 23/08/2024 | 23/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.84 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Sashpur Zone-B Water Supply Scheme | SM/17421 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF SASHPUR ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000305/2023-2024 | 1919/BQA | 13/07/2023 | 29/03/2026 | PRINCE INDUTRIES (INDIA) | 184.65 | 92.25 | 49.96 | 80
6 | BANKURA |  | Bankura Mechanical | Augmentation of Sashpur Zone-B Water Supply Scheme | SM/17421 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Sashpur (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000530/2023-2024 | 1894/BMD | 17/08/2023 | 02/06/2025 | M/S SAJAHAN CHOWDHURY | 75.78 | 42.72 | 56.38 | 60
7 | BANKURA |  | Bankura Division | Augmentation of Sashpur Zone-B Water Supply Scheme | SM/17421 | Augmentation | Construction of Boundary Wall and Pump House for Augmentation of Sashpur (Zone-B) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001379/2024-2025 | 24/BQA | 02/01/2025 | 02/04/2025 | SK FAZLUL ALAM | 12.94 | 0 | 0 | 70
Total | [13 empty] | 282.3 | 134.98 | 47.81