## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Somsar Water Supply Scheme | SM/17422 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 2526/BQA | 08/09/2023 | 08/09/2023 | Resource Division | 3.19 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Somsar Water Supply Scheme | SM/17422 | Augmentation | Augmentation of Somsar Water Supply Scheme |  |  | BILL/00190/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Somsar Water Supply Scheme | SM/17422 | Augmentation | Load enhancement charges for SOMSAR PH-I Water supply scheme under Bankura Mechanical Division PHE DTE |  |  | BILL/00434/2024-2025 | BP-2024-25-108 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.29 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Somsar Water Supply Scheme | SM/17422 | Augmentation | Load enhancement charges for SOMSAR PH-II water supply scheme under B.M.D P.H.E Dte |  |  | BILL/00441/2024-2025 | BP-2024-25-109 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.66 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Somsar Water Supply Scheme | SM/17422 | Augmentation | Sinking of 2 nos. 300mm X 200mm X 250m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe, Laying distribution system and platform for FHTC in connection with Jal Jeevan Mission (JJM) of Somsar W/S Scheme under Bishnupur Sub-Division of Bankura Division, PHE Dte. Block Name:- Indas, Location of OHR :-Somsar No. of Mouzas Covered :- 1 nos., Name of Mouzas & JL No.:-Somsar (2) Total No. House Hold | Assistant Engineer | Junior Engineer | ORD/000794/2022-2023 | 678/BQA | 28/03/2023 | 01/01/2026 | GOUTAM GHOSH | 81.88 | 20.38 | 24.88 | 80
6 | BANKURA |  | Bankura Mechanical | Augmentation of Somsar Water Supply Scheme | SM/17422 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Somsar piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Indus, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000461/2023-2024 | 1787/BMD | 01/08/2023 | 27/05/2024 | A.G.ENTERPRISE | 53.61 | 24.55 | 45.79 | 60
7 | BANKURA |  | Bankura Division | Augmentation of Somsar Water Supply Scheme | SM/17422 | Augmentation | Construction of boundary wall approx 150 mtr long of Somsar Piped water supply scheme (H/W Site) in Indas Block under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000210/2024-2025 | 1857/BQA | 12/07/2024 | 26/08/2024 | FAZLUR RAHAMAN BHANGI | 8.59 | 0 | 0 | 100
8 | BANKURA |  | Bankura Division | Augmentation of Somsar Water Supply Scheme | SM/17422 | Augmentation | Instalation of scheme information board for 3 nos. site of Augmentation of Indas Water Supply Scheme (SM/17684 ) & 2 nos. sites of Augmentation of Somsar Water Supply Scheme (SM/17422) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001822/2024-2025 | 543/VSD | 27/09/2024 | 12/10/2024 | PARTHA ROY | 0.75 | 0 | 0 | 0
Total | [13 empty] | 150.49 | 44.92 | 29.85