## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Panchal Zone-II Water Supply Scheme | SM/17423 | Augmentation | Augmentation of Panchal Zone-II Water Supply Scheme |  |  | BILL/00187/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Panchal Zone-II Water Supply Scheme | SM/17423 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Panchal (Zone-II) piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000463/2023-2024 | 1789/BMD | 01/08/2023 | 29/11/2023 | TAPAN KUMAR SARKAR | 41.85 | 16.61 | 39.68 | 40
3 | BANKURA |  | Bankura Mechanical | Augmentation of Panchal Zone-II Water Supply Scheme | SM/17423 | Augmentation | New Service connection for Panchal water supply scheme under Bankura Mechanical Division PHE Dte.(SM-17423) |  |  | BILL/00417/2024-2025 | BP-2024-25-97 | 04/07/2024 | 04/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Panchal Zone-II Water Supply Scheme | SM/17423 | Augmentation | New Service connection for Panchal Water Supply Scheme under BMD PHE Dte |  |  | BILL/00026/2024-2025 | 1 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.83 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation of Panchal Zone-II Water Supply Scheme | SM/17423 | Augmentation | New Service connection for Panchal Water Supply Scheme under BMD PHE Dte |  |  | BILL/00025/2024-2025 |  | 19/04/2024 | 19/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.83 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation of Panchal Zone-II Water Supply Scheme | SM/17423 | Augmentation | New Service connection for Sukhsayer water supply scheme under Bankura Mechanical Division PHE Dte. |  |  | BILL/00380/2024-2025 | BP-2024-25-85 | 11/06/2024 | 11/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.2 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation of Panchal Zone-II Water Supply Scheme | SM/17423 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PANCHAL ZONE-II PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000409/2023-2024 | 2094/BQA | 27/07/2023 | 01/11/2025 | M/S D.PALIT & CO. | 138.26 | 71.7 | 51.86 | 80
Total | [13 empty] | 196.46 | 88.31 | 44.95