## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17424 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000121/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.39 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17424 | Augmentation | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00135/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17424 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electro mechanical accessories for Augmentation work for Dadhimukha ( Zone-D) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000455/2023-2024 | 1781/BMD | 01/08/2023 | 29/11/2023 | SUNRISE ENGINEERING CORPORATION | 81.75 | 0 | 0 | 30
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17424 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro-mechanical accessories for Augmentation works at Rautara Pump house (Tail End) under Dadhimukha (Zone -D) and its Adjoing moujazs water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000154/2024-2025 | 497/BMD | 09/07/2024 | 01/11/2025 | GOENKA ENTERPRISE | 23.1 | 0 | 0 | 30
5 | BANKURA |  | Bankura Division | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17424 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000270/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.39 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17424 | Augmentation | Service connection charge for at Rautara tail end T/W under Dadhimukha (zone-D) water supply scheme Barjora block under BMD,PHE Dte.(SM/17424 ) |  |  | BILL/00347/2024-2025 | 12 | 24/07/2024 | 24/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17424 | Augmentation | Construction of Low Lift Pump House and Boundary Wall at Asnasole Mouza and Boundary Wall at Rautara Mouza under Augmentation of Dadhimukha (Zone- D) Water Supply Scheme. | Assistant Engineer |  | ORD/001404/2024-2025 | 47/BQA | 02/01/2025 | 02/04/2025 | SOUHARDYA BUSINESSLINE | 22.87 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17424 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Godardihi (Zone- E) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001179/2023-2024 | 431/BQA | 08/02/2024 | 09/03/2024 | LEMNISCATE | 2.31 | 0 | 0 | 100
9 | BANKURA |  | Bankura Division | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17424 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Dadhimukha (Zone- D) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001178/2023-2024 | 430/BQA | 08/02/2024 | 09/03/2024 | LEMNISCATE | 1.69 | 0 | 0 | 100
10 | BANKURA |  | Bankura Division | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17424 | Augmentation | Construction of Pump House with all allied works at Dadhimukha (Zone- D), OHR Site under Augmentation of Dadhimukha Water Supply Scheme under Jal Jeevan Mission (JJM) under Bankura Sadar Sub- Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000176/2024-2025 | 1851/BQA | 12/07/2024 | 16/05/2025 | SAYED PAHALOWAN | 18.37 | 0 | 0 | 100
Total | [13 empty] | 158 | 0 | 0