## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Chakuparsole Zone-A Water Supply Scheme | SM/17425 | Augmentation | Augmentation of Chakuparsole Zone-A Water Supply Scheme |  |  | BILL/00169/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Chakuparsole Zone-A Water Supply Scheme | SM/17425 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Existing TW I to IV for Augmentation of Chakuparsole and Adjoining mouza water supply scheme (Zone-A) Block-Bishnupurunder Under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000141/2024-2025 | 484/BMD | 09/07/2024 | 06/11/2024 | M/S NABIN GOPAL SENGUPTA | 40.43 | 24.39 | 60.33 | 100
3 | BANKURA |  | Bankura Mechanical | Augmentation of Chakuparsole Zone-A Water Supply Scheme | SM/17425 | Augmentation | Quotation for new serrvice connection at Chak Uparsole Z-A TW-II JL 135 Mouza Bhaluka.SM -17425 |  |  | BILL/01142/2024-2025 | BP-2024-25-282 | 21/11/2024 | 21/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.43 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Chakuparsole Zone-A Water Supply Scheme | SM/17425 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF CHAKUPARSOLE ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000390/2023-2024 | 2050/BQA | 24/07/2023 | 29/03/2026 | PRINCE INDUTRIES (INDIA) | 201.42 | 117.33 | 58.25 | 90
5 | BANKURA |  | Bankura Mechanical | Augmentation of Chakuparsole Zone-A Water Supply Scheme | SM/17425 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chakuparsole (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000518/2023-2024 | 1883/BMD | 17/08/2023 | 02/06/2026 | SUNRISE ENGINEERING CORPORATION | 71.39 | 0 | 0 | 75
6 | BANKURA |  | Bankura Mechanical | Augmentation of Chakuparsole Zone-A Water Supply Scheme | SM/17425 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Submersible Pump Motor set and other allied works at Prakash Zone-A & Chakuparsol Zone-A water supply scheme under Bishnupur Block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000552/2025-2026 | 640/BMD | 11/07/2025 | 09/10/2025 | MIK ENTERPRISES | 20.18 | 0 | 0 | 0
Total | [13 empty] | 346.34 | 141.72 | 40.92