## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Chakuparsole Zone-B Water Supply Scheme | SM/17426 | Augmentation | Augmentation of Chakuparsole Zone-B Water Supply Scheme |  |  | BILL/00170/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Chakuparsole Zone-B Water Supply Scheme | SM/17426 | Augmentation | Submission of quotation for new service connection at Mouza Upar Amdahara of Chakuparsole Zone-B W/S scheme Boosting TW-I. SM/17426. |  |  | BILL/00540/2024-2025 | BP-2024-25-209 | 03/09/2024 | 03/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.9 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Chakuparsole Zone-B Water Supply Scheme | SM/17426 | Augmentation | Submission of Quotation for new service connection at Mouza Phulboni of Chakuparsole Zone-B ws scheme.SM/17426 |  |  | BILL/00539/2024-2025 | BP-2024-25-208 | 03/09/2024 | 03/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.69 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Chakuparsole Zone-B Water Supply Scheme | SM/17426 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF CHAKUPARSOLE ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000499/2023-2024 | 2349/BQA | 14/08/2023 | 02/04/2025 | I.R.CONSTRUCTION | 177.27 | 60.48 | 34.12 | 70
5 | BANKURA |  | Bankura Mechanical | Augmentation of Chakuparsole Zone-B Water Supply Scheme | SM/17426 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Existing TW II to IV for Augmentation of Chakuparsole and Adjoining mouza water supply scheme (Zone-B) Block-Bishnupur under Under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000142/2024-2025 | 485/BMD | 09/07/2024 | 30/07/2025 | GOENKA ENTERPRISE | 34.36 | 0 | 0 | 100
6 | BANKURA |  | Bankura Division | Augmentation of Chakuparsole Zone-B Water Supply Scheme | SM/17426 | Augmentation | Instalation of scheme information board for 2 nos. sites of Augmentation of Prakash Zone-B Water Supply Scheme (SM/16945), 4 nos. sites of Augmentation of Chakuparsole Zone-B Water Supply Scheme (SM/17426 ) within Bishnupur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001803/2024-2025 | 532/VSD | 27/09/2024 | 12/10/2024 | SANTANU GARAI | 0.9 | 0 | 0 | 0
Total | [13 empty] | 219.62 | 60.48 | 27.54