## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Chuamasina Zone-B Water Supply Scheme | SM/17427 | Augmentation | Augmentation of Chuamasina Zone-B Water Supply Scheme |  |  | BILL/00167/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Chuamasina Zone-B Water Supply Scheme | SM/17427 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF CHUAMASINA ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000392/2023-2024 | 2052/BQA | 24/07/2023 | 01/04/2025 | SIB SANKAR CHOWDHURY | 155.9 | 41.21 | 26.44 | 65
3 | BANKURA |  | Bankura Mechanical | Augmentation of Chuamasina Zone-B Water Supply Scheme | SM/17427 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chuamasina (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000522/2023-2024 | 1886/BMD | 17/08/2023 | 02/06/2026 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 75.75 | 47.23 | 62.36 | 55
4 | BANKURA |  | Bankura Division | Augmentation of Chuamasina Zone-B Water Supply Scheme | SM/17427 | Augmentation | Construction of Pump House for Augmentation of Chuamosina (Zone-B) Piped Water Supply Scheme. | Assistant Engineer |  | ORD/001378/2024-2025 | 19/BQA | 02/01/2025 | 02/04/2025 | SANTI RANJAN MANDAL | 6.56 | 0 | 0 | 0
Total | [13 empty] | 239.7 | 88.45 | 36.9