## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). | SM/17428 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 3.54 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). | SM/17428 | Augmentation | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). |  |  | BILL/00157/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). | SM/17428 | Augmentation | Regarding permission and revision of estimate of permanent restroration work for the purpose of leakage repairing works on Rangamati-Asuria-Dejuri Road |  |  | BILL/00620/2023-2024 | FHTC/11 | 09/11/2023 | 09/11/2023 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 1.23 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). | SM/17428 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I)( Zone-III) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000298/2023-2024 | 1401/BMD | 18/07/2023 | 16/09/2023 | M.S. ENTERPRISE | 81.83 | 0 | 0 | 48
5 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). | SM/17428 | Augmentation | Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-III) | Assistant Engineer | Junior Engineer | ORD/000432/2023-2024 | 2266/BQA | 01/08/2023 | 27/04/2024 | SIB SANKAR CHOWDHURY | 255.5 | 0 | 0 | 50
6 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). | SM/17428 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End site for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I) (Zone-IA) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000337/2024-2025 | 519/BMD | 09/07/2024 | 06/11/2024 | SINHA ELECTRICALS | 11.28 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). | SM/17428 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories at Tail end site for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I) ( Zone-III) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000155/2024-2025 | 498/BMD | 09/07/2024 | 06/11/2024 | S.DUTTA | 13.17 | 0 | 0 | 38
8 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). | SM/17428 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000268/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 3.54 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). | SM/17428 | Augmentation | Construction of High lift Pump House, 450 cum OHR along with soil investigation work, boundary wall and laying of rising main under Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III) | Assistant Engineer |  | ORD/000535/2025-2026 | 2154/BQA | 30/10/2025 | 28/01/2026 | CHAKRABORTTI ENTERPRISE | 166.89 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). | SM/17428 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001187/2023-2024 | 439/BQA | 08/02/2024 | 09/03/2024 | LEMNISCATE | 1.54 | 0 | 0 | 100
Total | [13 empty] | 539.52 | 0 | 0