## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | Sinking of 3 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-N (Khejuria) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000784/2022-2023 | 674/BQA | 28/03/2023 | 17/02/2027 | SWAPAN KUMAR CHANDRA | 92.14 | 29.91 | 32.46 | 80
2 | BANKURA |  | Bankura Division | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | Work Order for Supply, Delivery and Stacking of Sluice Valve of Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000125/2023-2024 | 127/KSD | 25/05/2023 | 09/06/2023 | SSPR VALVE MANUFACTURING PVT. LTD. | 0.94 | 0.94 | 100 | 20
3 | BANKURA |  | Bankura Division | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | Sinking of 4 (Four) Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction of 6 (Six) Nos. Pump Houses with ancillary works in different mouzas of Zone-N (Khejuria) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001153/2023-2024 | 357/BQA | 06/02/2024 | 03/04/2025 | TARINI CHARAN UPADHYAY | 56.71 | 6.27 | 11.06 | 55
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of High lift and Low lift Pumping machineries with other electro-mechanical accessories at tail end and CWR site for Augmentation works for Khejuria (Zone- N) ( Boosting at OHR Site) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Bankura Mechanical Division, PHE Dte. Block : Ranibandh , Dist: Bankura | Driller-in-Charge | Junior Engineer | ORD/000170/2024-2025 | 512/BMD | 09/07/2024 | 29/06/2026 | DEBJYOTI BASU | 92.97 | 0 | 0 | 68
5 | BANKURA |  | Bankura Division | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | Laying HDPE pipeline from Karapara village to Bansdiha village with all allied works of Zone-N (Khejuria) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001157/2023-2024 | 369/BQA | 06/02/2024 | 07/03/2024 | DAUD ALI KHAN | 13.37 | 13.37 | 99.99 | 80
6 | BANKURA |  | Bankura Division | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | Laying HDPE pipeline from Karapara village to Bansdiha village with all allied works of Zone-N (Khejuria) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001156/2023-2024 | 368/BQA | 06/02/2024 | 07/03/2024 | MANAS DEY | 13.37 | 13.36 | 99.87 | 80
7 | BANKURA |  | Bankura Division | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | Construction of CWR (100 Cum.) along with all allied works for Augmentation works for Zone-N (Khejuria) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000067/2024-2025 | 1522/BQA | 19/06/2024 | 02/04/2025 | PRADIP CHAKRABORTY | 22.53 | 0 | 0 | 90
8 | BANKURA |  | Bankura Division | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000176/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 1.39 | 0 | 0 | 0
9 | BANKURA |  | Bankura Mechanical | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | New service connection at P/H-I of Khejuria |  |  | BILL/01149/2024-2025 | BP-2024-25-281 | 21/11/2024 | 21/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.8 | 0 | 0 | 0
10 | BANKURA |  | Bankura Mechanical | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | New service connection at T/W-III of Khejuria |  |  | BILL/01146/2024-2025 | BP-2024-25-271 | 19/11/2024 | 19/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.71 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | Ranibandh - Jhilimili Road from Ch.16.048 km to Ch.16.148 km, from Ch.16.810 km to Ch.16.920 km, Restoration work damage by P.H.E Department by laying Pipe line under Bankura Highway Division in the District of Bankura. Augmentation of Khejuria (Zone-N) W/S Scheme (SM/17429) |  |  | BILL/01246/2024-2025 | BP-347/2024-25 | 03/10/2024 | 03/10/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 3.88 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | Ranibandh - Jhilimili Road from Ch.16.048 km to Ch.16.148 km, from Ch.16.810 km to Ch.16.920 km, Restoration work damage by P.H.E Department by laying Pipe line under Bankura Highway Division in the District of Bankura. Augmentation of Khejuria (Zone-N) W/S Scheme (SM/17429) |  |  | BILL/01031/2024-2025 |  | 28/09/2024 | 28/09/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 3.88 | 0 | 0 | 0
13 | BANKURA |  | Bankura Mechanical | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | New service connection at T/W-IV of Khejuria |  |  | BILL/01147/2024-2025 | BP-2024-25-272 | 19/11/2024 | 19/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.46 | 0 | 0 | 0
14 | BANKURA |  | Bankura Mechanical | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Khejura (Zone N) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Driller-in-Charge | Junior Engineer | ORD/000044/2025-2026 | 248/BMD | 14/05/2025 | 12/08/2025 | M.S. ENTERPRISE | 29.11 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | Work Order for Installation of scheme information board for 4 nos. site of Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) (SM/17429) within Ranibandh Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001916/2024-2025 | 160\KSD | 07/03/2025 | 17/03/2025 | S. B. CONSTRUCTION | 0.6 | 0 | 0 | 90
16 | BANKURA |  | Bankura Mechanical | Augmentation works for Khejuria (Zone- N) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17429 | Augmentation | New service Connection at Khejuria T/W-II |  |  | BILL/01480/2024-2025 | BP-2024-25-370 | 07/02/2025 | 07/02/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.88 | 0 | 0 | 0
Total | [13 empty] | 334.73 | 63.85 | 19.07