## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) | SM/17430 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-IIB (Hetiasol) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000606/2022-2023 | 559/BQA | 17/03/2023 | 01/05/2023 | SK. SAHAJAHAN | 32.01 | 28.37 | 88.65 | 50
2 | BANKURA |  | Bankura Division | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) | SM/17430 | Augmentation | Sinking of 3 (Three) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works for Zone-IIB (Hetiasol) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001130/2023-2024 | 202/BQA | 24/01/2024 | 08/04/2024 | UTTAM KUMAR SINHAMAHAPATRA | 22.34 | 20.94 | 93.7 | 90
3 | BANKURA |  | Bankura Division | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) | SM/17430 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 1.91 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) | SM/17430 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Hetiasol (Zone IIB) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Driller-in-Charge | Junior Engineer | ORD/000041/2025-2026 | 245/BMD | 14/05/2025 | 12/08/2025 | TAPAN KUMAR DEY | 28.18 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) | SM/17430 | Augmentation | Laying HDPE pipeline from Dakai to Madhabpur village to increase pressure at Madhabpur Village in connection with Augmentation of Hetiasole (Zone-IIB) Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000338/2024-2025 | 2303/BQA | 04/09/2024 | 02/02/2025 | JAGABANDHU MONDAL | 2.78 | 2.65 | 95.18 | 70
6 | BANKURA |  | Bankura Mechanical | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) | SM/17430 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low lift pumping machineries and other electromechanical accessories for Dahala W.S Scheme under Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Driller-in-Charge | Junior Engineer | ORD/000151/2024-2025 | 494/BMD | 09/07/2024 | 02/06/2025 | ABHIJIT MUKHERJEE | 65.43 | 0 | 0 | 63
Total | [13 empty] | 152.66 | 51.96 | 34.04