## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Jambedia(Zone-Q) under Khatra-Hirbandh-Ranibandh Water Supply Scheme(BRGF ph-I) | SM/17432 | Augmentation | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-Q (Jambedia) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000817/2022-2023 | 722/BQA | 30/03/2023 | 28/06/2023 | SHYAMAL KUMAR DAS | 38.54 | 0 | 0 | 80
2 | BANKURA |  | Bankura Division | Augmentation works for Jambedia(Zone-Q) under Khatra-Hirbandh-Ranibandh Water Supply Scheme(BRGF ph-I) | SM/17432 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000174/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 1.72 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Jambedia(Zone-Q) under Khatra-Hirbandh-Ranibandh Water Supply Scheme(BRGF ph-I) | SM/17432 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Jambedia (Zone Q) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Driller-in-Charge | Junior Engineer | ORD/000051/2025-2026 | 250/BMD | 14/05/2025 | 12/08/2025 | JAL PRAVAHIKA PVT LTD | 25.68 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Jambedia(Zone-Q) under Khatra-Hirbandh-Ranibandh Water Supply Scheme(BRGF ph-I) | SM/17432 | Augmentation | Laying HDPE pipeline from Hatirampur Canal Bridge to Baharamuri village with all allied works of Zone-Q (Jambedia) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000343/2024-2025 | 2326/BQA | 06/09/2024 | 23/07/2025 | AKRAM BHANGI | 3.34 | 0 | 0 | 90
Total | [13 empty] | 69.28 | 0 | 0