## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000397/2023-2024 | 2082/BQA | 27/07/2023 | 22/04/2024 | UNIVERSAL CONSTRUCTION | 160.24 | 37.9 | 23.65 | 35
2 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Formal work order for the work of Providing and Installation of High lift & Low lift pumping machineries and other electromehanical accessories for Augmentation of Simlapal piped water supply scheme for providing FHTC, Block - Simlapal Dist - Bankura under Bankura Mechanical Division, PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000451/2023-2024 | 1792/BMD | 01/08/2023 | 17/01/2026 | A.K.INDUSTRIES | 127.79 | 0 | 0 | 85
3 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Baricha Zone-B and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000576/2023-2024 | 2037/BMD | 01/09/2023 | 15/10/2026 | S.P. CONSTRUCTION | 83.04 | 43.68 | 52.6 | 39
4 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. for the period from 01/01/2024 to 30/06/2024. | Assistant Engineer | Junior Engineer | ORD/001171/2023-2024 | 370/KSD | 29/12/2023 | 28/06/2024 | BISWAJIT LAI | 0.86 | 2.02 | 234.22 | 90
5 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. |  |  | BILL/00217/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Work Order for Laying of HDPE pipeline, Construction of Valve Chamber for Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000161/2024-2025 | 1826/BQA | 12/07/2024 | 02/11/2025 | SUBHADIP KOLE | 69.99 | 0 | 0 | 70
7 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Baricha Zone - B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000385/2024-2025 | 2433/BQA | 25/09/2024 | 25/10/2024 | CARTO | 1.89 | 1.84 | 97.13 | 90
8 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000186/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 2.34 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 350 Cum., staging height 20 Mtr.), Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Baricha, Zone-B water Supply Scheme under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001969/2024-2025 | 665/BQA | 12/03/2025 | 01/08/2025 | DAUD ALI KHAN | 13.59 | 0 | 0 | 90
10 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Repair and Maintenance work of the Road from Bhutsahar Nadighat to Parasole village under Simlapal Block in the District of Bankura ,Vide Package No- Road Length-4.5 Km. ( Augmentation of water supply scheme for Baricha (Zone-B) under Simlapal water supply scheme (BRGF Ph-I). |  |  | BILL/01439/2024-2025 | BP/569/2024-25 | 28/03/2025 | 28/03/2025 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 0.53 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Repair and Maintenance work of the Road from Bhutsahar Nadighat to Parasole village under Simlapal Block in the District of Bankura ,Vide Package No- Road Length-4.5 Km. ( Augmentation of water supply scheme for Baricha (Zone-B) under Simlapal water supply scheme (BRGF Ph-I). |  |  | BILL/02120/2024-2025 | BP-536/2024-25 | 23/03/2025 | 23/03/2025 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 1.04 | 0 | 0 | 0
Total | [13 empty] | 462.83 | 85.44 | 18.46