## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. |  |  | BILL/00217/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. for the period from 01/01/2024 to 30/06/2024. | Assistant Engineer | Junior Engineer | ORD/001171/2023-2024 | 370/KSD | 29/12/2023 | 28/06/2024 | BISWAJIT LAI | 0.86 | 2.02 | 234.22 | 90
3 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000186/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 2.34 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000397/2023-2024 | 2082/BQA | 27/07/2023 | 22/04/2024 | UNIVERSAL CONSTRUCTION | 160.24 | 37.9 | 23.65 | 35
5 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Formal work order for the work of Providing and Installation of High lift & Low lift pumping machineries and other electromehanical accessories for Augmentation of Simlapal piped water supply scheme for providing FHTC, Block - Simlapal Dist - Bankura under Bankura Mechanical Division, PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000451/2023-2024 | 1792/BMD | 01/08/2023 | 17/01/2026 | A.K.INDUSTRIES | 127.79 | 0 | 0 | 85
6 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | SM/17434 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Baricha Zone-B and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000576/2023-2024 | 2037/BMD | 01/09/2023 | 30/12/2023 | S.P. CONSTRUCTION | 83.04 | 43.68 | 52.6 | 39
Total | [13 empty] | 375.79 | 83.6 | 22.25